## Sprint 1 Backlog
|  | Role | Activity | Entity | SP
CRUD Dialog | As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Configurationitem | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Configurationitemtype | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Configurationitemclass | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Configurationitemstatus | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Configurationitemrepository | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Configurationitemcategory | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Contract | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Contractcatalogue | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Contractcategory | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Contractclass | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Contractrepository | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Contracttype | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Service | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Servicecatalogue | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Servicecataloguecategory | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Servicecatalogueclass | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Servicecataloguetype | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Servicecategory | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Serviceclass | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Serviceportfolio | 8
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Serviceportfoliocategory | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Serviceportfolioclass | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Serviceportfoliodimensions | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Serviceportfoliodimensionstype | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Serviceportfoliogroup | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Serviceportfoliotype | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Servicequality | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Servicequalitycategory | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Servicequalityclass | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Servicequalitytype | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Servicerepository | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Servicestatus | 5
| As a | User | I should be able to Maintain,Copy,Create,Display,Edit | Servicetype | 5
View Service portfolio | As a | Service Portfolio Owner | I should be able to view the manage operations tab under my work in the login landing page |  | 1
| As a | Service Portfolio Owner | I should be able to view the option of service portfolio when I click manage operations tab. |  | 1
| As a | Service Portfolio Owner | I should be able to click on service portfolio and land on the portfolio list page. |  | 1
| As a | Service Portfolio Owner | I should be able to view all my portfolio on the portfolio list page |  | 1
| As a | Service Portfolio Owner | I should be able to filter the portfolio based on portfolio type |  | 1
| As a | Service Portfolio Owner | I should be able to filter the portfolio based on portfolio dimension type |  | 1
| As a | Service Portfolio Owner | I should be able to filter the portfolio with respect to dimensions. |  | 3
| As a | Service Portfolio Owner | I should be able to filter the portfolio based on multiple portfolio type |  | 1
| As a | Service Portfolio Owner | I should be able to filter the portfolio based on multiple dimension type |  | 3
| As a | Service Portfolio Owner | I should be able to filter the portfolio based on multiple dimension |  | 1
| As a | Service Portfolio Owner | I should be able to search the portfolio by keyword or name from the search bar |  | 1
| As a | Service Portfolio Owner | I should be navigated to the dashboard page once I click on selected portfolio |  | 1
| As a | Service Portfolio Owner | I should be able to view all combinations of dimension and dimension type |  | 1
| As a | Service Portfolio Owner | I should be able to revert any selection made inside the filter and update the lists. |  | 1
| As a | Service Portfolio Owner | I should be able to sort the portfolio list by different attributes of a portfolio |  | 1
View Service in a Service Portfolio | As a | Service Portfolio Owner | I should be directed to dashboard page once I select a portfolio |  | 1
| As a | Service Portfolio Owner | I should be able to get the overview of the portfolio on the dashboard |  | 1
| As a | Service Portfolio Owner | I should be able to click on Service attributes to view their details |  | 1
| As a | Service Portfolio Owner | I should be able to view the list of services in a service portfolio |  | 1
| As a | Service Portfolio Owner | I should be able to filter the services based on different service attributes |  | 1
| As a | Service Portfolio Owner | I should be able to filter the services by service type |  | 1
| As a | Service Portfolio Owner | I should be able to filter the service by service type |  | 1
| As a | Service Portfolio Owner | I should be able to search for services by search keyword |  | 1
| As a | Service Portfolio Owner | I should be able to view the updated lists after the filters are applied |  | 1
| As a | Service Portfolio Owner | I should be able to click on service to get the service overview |  | 1
|  |  |  | Total | 197
Total No of Working day in Sprint 1 = 16 Days
No if of Hours per day = 8 Hr
No of Resource = 5
Total No of Man Hour for sprint 1= 16*8*5 = 640
Effort per person for Sprint Planning and retrospective = 1 day = 8Hr
Total effort for Sprint Planning and Retrospective = 8*5 = 40 Hr
Effort per person for Stand up meeting, Work Division and issuse resolution = 1 hr/day
Effort per Person for the sprint = 16 hr
Effort for the team = 16*5 = 80 Hr
Effective Working hour = 640 - (80+40) = 520
Total Story points allocated in sprint 1 = 197
As per Instant Edge standards 1 Story point = 2Hr
so hours per point = 2.38 Hr
As we are doing the sprint for the first time Hrs allocated = 3hrs /point

## Sprint 1 Burn Down Chart
Days | Planned Hours Burndown | Actual Hours burndown | Dates
0 | 582 | 582 | 20/09/2016
1 | 542 | 550 | 23/09/2016
2 | 502 | 518 | 27/09/2016
3 | 462 | 482 | 30/09/2016
4 | 422 | 444 | 2016-04-10
5 | 382 | 404 | 2016-07-10
6 | 342 | 364 | 2016-11-10
7 | 302 | 344 | 2016-12-10
8 | 262 | 368 | 18/10/2016
9 | 220 | 324 | 19/10/2016
10 | 180 | 280 | 25/10/2016
11 | 140 | 236 | 26/10/2016
12 | 100 | 192 | 2016-01-11
13 | 60 | 148 | 2016-02-11
14 | 20 | 100 | 2016-04-11
15 | 0 | 56 | 2016-05-11
16 |  | 12 | 2016-08-11
2016-09-11