## Sprint 2
PUSH NOTIFICATION
SL NO | User Story | Story Point | Task | No of Hours | Planned start Date | Planned End date | Actual Start Date | Actual End Date | Resource
1 | As a User, I want to access the platform on my Android mobile so that I can get updates instantly | 13
|  |  | Create an cross platform mobile application in Microsoft Xamarin(android) . | 16 | 16/12/2016 | 19/12/2016 |  |  | Zhao
|  |  | Create a Xamarin project with Android App, | 5 | 20/12/2016 | 20/12/2016 |  |  | Zhao
|  |  | Create Mobile Activity to display login page in android | 5 | 20/12/2016 | 21/12/2016 |  |  | Zhao
|  |  | Create Mobile Activity to display list of inbox items in android | 5 | 21/12/2016 | 21/12/2016 |  |  | Zhao
|  |  | Create Mobile Activity to display details of notifications in android | 8 | 22/12/2016 | 22/12/2016 |  |  | Zhao
2 | As a User, I want to access the platform on my iOS mobile so that I can get updates instantly | 13
|  |  | Create an cross platform mobile application in Microsoft Xamarin (ios). | 16 | 16/12/2016 | 19/12/2016 |  |  | Vignesh
|  |  | Create a Xamarin project with , iOS App and a Shared Code base | 5 | 20/12/2016 | 20/12/2016 |  |  | Vignesh
|  |  | Create Storyboard item to display login page in iOS | 5 | 20/12/2016 | 21/12/2016 |  |  | Vignesh
|  |  | Create Storyboard item to display list of inbox items in iOS | 5 | 21/12/2016 | 21/12/2016 |  |  | Vignesh
|  |  | Create Storyboard item to display details of notifications in iOS | 8 | 22/12/2016 | 22/12/2016 |  |  | Vignesh
3 | As a User, I should be able to login to Instant Edge platform on my android mobile application | 5 | Implement JWT token based authentication in server side. | 1 | 22/12/2016 | 22/12/2016 |  |  | Zhao
|  |  | Create a rest end point to authenticate users and generate JWT | 0.5 | 23/12/2016 | 23/12/2016 |  |  | Zhao
|  |  | Develop mobile UI to get user credentials | 0.5 | 23/12/2016 | 23/12/2016 |  |  | Zhao
|  |  | Communicate with instant edge server and obtain JWT | 1 | 23/12/2016 | 23/12/2016 |  |  | Zhao
|  |  | Create rest end point to obtain FCM token from devices | 1 | 23/12/2016 | 23/12/2016 |  |  | Zhao
|  |  | Register the FCM token with users list of devices | 5 | 23/12/2016 | 23/12/2016 |  |  | Zhao
|  |  | Refresh FCM token in fixed intervals | 3 | 27/12/2016 | 27/12/2016 |  |  | Zhao
|  |  | Send a IE generated Device token back to devices | 1 | 27/12/2016 | 27/12/2016 |  |  | Zhao
|  |  | From the device send local device token to FCM and obtain FCM token | 1 | 27/12/2016 | 27/12/2016 |  |  | Zhao
|  |  | Send the FCM token to server to register for Push Notifications | 0.5 | 27/12/2016 | 27/12/2016 |  |  | Zhao
|  |  | Obtain Server generated Device token fro deregistration in the future | 0.5 | 27/12/2016 | 27/12/2016 |  |  | Zhao
4 | As a User, I should be able to login to Instant Edge platform on my iOS mobile application | 5 | Implement JWT token based authentication in server side. | 1 | 22/12/2016 | 22/12/2016 |  |  | Vignesh
|  |  | Create a rest end point to authenticate users and generate JWT | 0.5 | 23/12/2016 | 23/12/2016 |  |  | Vignesh
|  |  | Develop mobile UI to get user credentials | 0.5 | 23/12/2016 | 23/12/2016 |  |  | Vignesh
|  |  | Communicate with instant edge server and obtain JWT | 1 | 23/12/2016 | 23/12/2016 |  |  | Vignesh
|  |  | Create rest end point to obtain FCM token from devices | 1 | 23/12/2016 | 23/12/2016 |  |  | Vignesh
|  |  | Register the FCM token with users list of devices | 5 | 23/12/2016 | 23/12/2016 |  |  | Vignesh
|  |  | Refresh FCM token in fixed intervals | 3 | 27/12/2016 | 27/12/2016 |  |  | Vignesh
|  |  | Send a IE generated Device token back to devices | 1 | 27/12/2016 | 27/12/2016 |  |  | Vignesh
|  |  | From the device send local device token to FCM and obtain FCM token | 1 | 27/12/2016 | 27/12/2016 |  |  | Vignesh
|  |  | Send the FCM token to server to register for Push Notifications | 0.5 | 27/12/2016 | 27/12/2016 |  |  | Vignesh
|  |  | Obtain Server generated Device token fro deregistration in the future | 0.5 | 27/12/2016 | 27/12/2016 |  |  | Vignesh
5 | As a User, I should be able to view my dashboard when I login to the mobile application | 5 | Design the browser wrapper | 3 | 27/12/2016 | 28/12/2016 |  |  | Zhao
|  |  | Create a browser wrapper and set URL as IE dashboard page | 5 | 28/12/2016 | 28/12/2016 |  |  | Zhao
|  |  | Create a new session in IE using JWT | 2 | 28/12/2016 | 28/12/2016 |  |  | Zhao
|  |  | Build and set cookie for the wrapper | 2 | 29/12/2016 | 29/12/2016 |  |  | Zhao
|  |  | Load the URL | 1 | 29/12/2016 | 29/12/2016 |  |  | Zhao
|  |  | Test the URL | 2 | 29/12/2016 | 29/12/2016 |  |  | Zhao
6 | As a User, I want to receive a notification when I receive a new item in my unified box, so that I can handle it on time. | 5 | Create a new FCM message | 5 | 27/12/2016 | 28/12/2016 |  |  | Vignesh
|  |  | Send FCM message using serverID, generated during FCM account creation | 5 | 28/12/2016 | 28/12/2016 |  |  | Vignesh
|  |  | Test the iOS Feature | 3 | 28/12/2016 | 29/12/2016 |  |  | Vignesh
|  |  | Test the Android Feature | 2 | 29/12/2016 | 29/12/2016 |  |  | Vignesh
7 | As a User I should be able to logout from the mobile application | 3 | Send IE Generated device token to IE Server's logout endpoint | 3 | 29/12/2016 | 29/12/2016 |  |  | Zhao
|  |  | Create rest end point to receive logout requests and deregister device token from the users list of devices | 2 | 30/12/2016 | 30/12/2016 |  |  | Zhao
|  |  | Clear all user data from device | 2 | 30/12/2016 | 30/12/2016 |  |  | Zhao
|  |  | Test logout functionality | 2 | 30/12/2016 | 30/12/2016 |  |  | Zhao
8 | As a User, I want to click on the notification, so that I can be redirected to my unified inbox | 3 | Design the wrapper functionality | 3 | 29/12/2016 | 29/12/2016 |  |  | Vignesh
|  |  | Redirect to the wrapper when a notification is clicked | 2 | 30/12/2016 | 30/12/2016 |  |  | Vignesh
|  |  | Login automatically using JWT | 2 | 30/12/2016 | 30/12/2016 |  |  | Vignesh
|  |  | Test the wrapper functionality | 2 | 30/12/2016 | 30/12/2016 |  |  | Vignesh
INCIDENT MANAGEMENT |  | Story Point
9 | As a User, I want redesign the Actor Group Determination table , so as to avoid too much scrolling in the dialogue | 13 | Designing the UI for Actor Group Determination | 7 | 19/12/2016 | 19/12/2016 |  |  | vrinda
|  |  | Understanding the variations in the existing system | 6 | 19/12/2016 | 2016-12-20 |  |  | vrinda
|  |  | Make user select model and them select procedure | 5 | 2016-12-20 | 2016-12-21 |  |  | vrinda
|  |  | Minimising use of scrollers | 5 | 2016-12-21 | 2016-12-21 |  |  | vrinda
|  |  | Making efficient use of Tabs | 6 | 2016-12-21 | 2016-12-22 |  |  | vrinda
|  |  | Prototyping page "actorgroupDetermination.xhtml" | 4 | 2016-12-22 | 2016-12-23 |  |  | vrinda
|  |  | Prototyping "actorgroupDeterminationList.xhtml" | 6 | 2016-12-23 | 2016-12-23 |  |  | vrinda
10 | As an Architect, I want to be able to easily maintain the Actor Group Determination (AGD) without scrolling too much | 13 | Create page for "actorgroupDetermination" | 7 | 19/12/2016 | 19/12/2016 |  |  | Rameswari
|  |  | Use tabs instead of scroller | 8 | 2016-12-20 | 2016-12-20 |  |  | Rameswari
|  |  | Create controller "actorActorgroupAssignmentManagedBean" | 4 | 2016-12-20 | 2016-12-21 |  |  | Rameswari
|  |  | Change page "actorgroupDetermination.xhtml" | 5 | 2016-12-21 | 2016-12-21 |  |  | Rameswari
|  |  | Create controller actorgroupdeterminationManagedBean" | 8 | 2016-12-22 | 2016-12-22 |  |  | Rameswari
|  |  | Test the Actor Group Determination Table | 4 | 2016-12-23 | 2016-12-23 |  |  | Rameswari
|  |  | Regression test the page navigation from other pages | 3 | 2016-12-23 | 2016-12-23 |  |  | Rameswari
11 | As a Developer, I should place the edit buttons in such a way that they are consistent throughout the application | 5 | Change the page for "Assign FlowModelFlowProcedureDetermination" | 5 | 2016-12-23 | 2016-12-27 |  |  | vrinda
|  |  | Change the page for "FlowModel FlowType assignment" | 4 | 2016-12-27 | 2016-12-27 |  |  | vrinda
|  |  | Change the page for "Create FlowModel" | 3 | 2016-12-28 | 2016-12-28 |  |  | vrinda
|  |  | Test the Functionality | 3 | 2016-12-28 | 2016-12-28 |  |  | vrinda
12 | As a developer, I should change all the flow type to type and flow model to model | 5 | Change the page for "Create Flowtype" | 5 | 2016-12-23 | 2016-12-24 |  |  | Rameswari
|  |  | Change the page for "Create FlowModel" | 4 | 2016-12-27 | 2016-12-27 |  |  | Rameswari
|  |  | Change the page for "Assign FlowModelFlowProcedureDetermination" | 3 | 2016-12-28 | 2016-12-28 |  |  | Rameswari
|  |  | Change the page for "FlowModel FlowType assignment" | 3 | 2016-12-28 | 2016-12-28 |  |  | Rameswari
13 | As a developer, I should be sure that the cancel button works consistently for all the pages | 3 | Changes in page for "Maintain Flowfieldgroup" | 3 | 2016-12-28 | 2016-12-29 |  |  | vrinda
|  |  | Changes in page for "Maintain Actorgroup" | 2 | 2016-12-29 | 2016-12-29 |  |  | vrinda
|  |  | Testing the button in all the pages | 4 | 2016-12-29 | 2016-12-29 |  |  | vrinda
14 | As a developer, I want to be sure that the delete button in Assignment of Flow Step to Flow Procedure should delete the Step. | 3 | Assignment of Flow Step to Flow Procedure | 3 | 2016-12-28 | 2016-12-29 |  |  | Rameswari
|  |  | View the selected procedure | 2 | 2016-12-29 | 2016-12-29 |  |  | Rameswari
|  |  | link the step to procedure | 2 | 2016-12-29 | 2016-12-29 |  |  | Rameswari
|  |  | Delete the step within the procedure | 1 | 2016-12-29 | 2016-12-29 |  |  | Rameswari
|  |  | Testing the button in all the pages | 1 | 2016-12-29 | 2016-12-29 |  |  | Rameswari
15 | As a developer, I should differentiate Message overview, Attachment and message History , so as not to confuse the user | 5 | Changes in Create Incident | 4 | 2016-12-29 | 30/12/2016 |  |  | vrinda
|  |  | Changes in "Create Incident Managed bean" | 4 | 30/12/2016 | 30/12/2016 |  |  | vrinda
|  |  | Changes in "Create Flow Procedure Managed Bean" | 3 | 30/12/2016 | 2016-12-31 |  |  | vrinda
|  |  | Changes in "Flow procedure exception" | 2 | 2016-12-31 | 2016-12-31 |  |  | vrinda
|  |  | Changes in "Flow procedure service" | 1 | 2016-12-31 | 2016-12-31 |  |  | vrinda
|  |  | Testing the functionality | 1 | 2016-12-31 | 2016-12-31 |  |  | vrinda
16 | As a developer, I should have some for Assignment of Flow Model to Flow Type the flow model list | 5 | Assignment of "FlowModel FlowType" | 4 | 2016-12-29 | 30/12/2016 |  |  | Rameswari
|  |  | Assign flow procedure to model page. | 4 | 30/12/2016 | 30/12/2016 |  |  | Rameswari
|  |  | Changes in page for "Create Flowfieldgroup" | 4 | 30/12/2016 | 2016-12-31 |  |  | Rameswari
|  |  | Testing the button in all the pages | 3 | 2016-12-31 | 2016-12-31 |  |  | Rameswari
Total No of Working day in Sprint 2 = Days
No if of Hours per day = 8 Hr
No of Resource = 4
Total No of Man Hour for sprint 1= 10*8*4 = 320
Effort per person for Sprint Planning and retrospective =2 day = 8Hr
Total effort for Sprint Planning and Retrospective = 8*4 * 2= 64 Hr
Requirement gathering , Userstories and sprint backlog 3 day = 3*4*8 = 96
Analysis modeling = 2*4*8 = 64
Design modeling= 2*4*8 = 64
Effort per person for Stand up meeting, Work Division and issuse resolution = 1 hr/day
Effort per Person for the sprint = 16 hr
Effort for the team = 16*5 = 80 Hr
Effective Working hour = 640 - (320) = 320
Total Story points allocated in sprint 2 = 104
As per Instant Edge standards 1 Story point = 3Hr
so hours per point = 312 Hr

## Sprint 3
Sl No | User Story | Story Point | Task | No of Hours | Planned start Date | Planned End date | Actual start Date | Actual End date | Resource
1 | As a user I should be able to configure FlowType of an incident | 13 | Create page for "Create Flowtype" | 2 | 2017-09-01 | 2017-09-01 |  |  | Rameswari
|  |  | Create page for "Edit Flowtype" | 3 | 2017-09-01 | 2017-09-01 |  |  | Rameswari
|  |  | Create page for "Display Flowtype" | 1 | 2017-09-01 | 2017-09-01 |  |  | Rameswari
|  |  | Create page for "Copy Flowtype" | 1 | 2017-09-01 | 2017-09-01 |  |  | Rameswari
|  |  | Create page for "Maintain Flowtype" | 1 | 2017-09-01 | 2017-09-01 |  |  | Rameswari
|  |  | Create page for "FlowtypeList " | 1 | 2017-10-01 | 2017-10-01 |  |  | Rameswari
|  |  | Create controller "FlowtypeManagedBean" | 8 | 2017-10-01 | 2017-11-01 |  |  | Rameswari
|  |  | Create exceptions for "Flowtype" | 1 | 2017-11-01 | 2017-11-01 |  |  | Rameswari
|  |  | Create service interface "FlowtypeService" | 8 | 2017-11-01 | 2017-12-01 |  |  | Rameswari
|  |  | Create service "DefaultFlowtypeService" | 8 | 2017-12-01 | 13/01/2017 |  |  | Rameswari
|  |  | Create domain entity Flowtype" | 1 | 13/01/2017 | 13/01/2017 |  |  | Rameswari
|  |  | Test Flowtype | 4 | 13/01/2017 | 13/01/2017 |  |  | Rameswari
2 | As a user I chould be able to configure FlowModel of an incident | 8 | Create page for "Create FlowModel" | 1 | 13/01/2017 | 13/01/2017 |  |  | Rameswari
|  |  | Create page for "Edit Flowmodel" | 1 | 16/01/2017 | 16/01/2017 |  |  | Rameswari
|  |  | Create page for "Display Flowmodel" | 1 | 16/01/2017 | 16/01/2017 |  |  | Rameswari
|  |  | Create page for "Copy Flowmodel" | 1 | 16/01/2017 | 16/01/2017 |  |  | Rameswari
|  |  | Create page for "Maintain FlowModel" | 1 | 16/01/2017 | 16/01/2017 |  |  | Rameswari
|  |  | Create page for "FlowmodelList " | 1 | 16/01/2017 | 16/01/2017 |  |  | Rameswari
|  |  | Create controller "FlowmodelManagedBean" | 4 | 16/01/2017 | 17/01/2017 |  |  | Rameswari
|  |  | Create exceptions for "Flowmodel" | 1 | 17/01/2017 | 17/01/2017 |  |  | Rameswari
|  |  | Create service interface "FlowmodelService" | 4 | 17/01/2017 | 17/01/2017 |  |  | Rameswari
|  |  | Create service "DefaultFlowmodelService" | 4 | 17/01/2017 | 18/01/2017 |  |  | Rameswari
|  |  | Create domain entity Flowmodel" | 1 | 18/01/2017 | 18/01/2017 |  |  | Rameswari
|  |  | Test Flowmodel | 4 | 18/01/2017 | 18/01/2017 |  |  | Rameswari
3 | As a user I should be able to assign Flow model to Flow Type | 5 | Create page for "FlowModel FlowType assignment" | 1 | 18/01/2017 | 18/01/2017 |  |  | Rameswari
|  |  | Create controller "FlowmodelFlowTypeManagedBean" | 4 | 19/01/2017 | 19/01/2017 |  |  | Rameswari
|  |  | Create exceptions for "FlowmodelFlowtype" | 1 | 19/01/2017 | 19/01/2017 |  |  | Rameswari
|  |  | Create service interface "FlowmodelFlowtypeService" | 3 | 19/01/2017 | 19/01/2017 |  |  | Rameswari
|  |  | Create service "DefaultFlowmodelFlowtypeService" | 3 | 20/01/2017 | 20/01/2017 |  |  | Rameswari
|  |  | Create domain entity FlowmodelFlowtype" | 1 | 20/01/2017 | 20/01/2017 |  |  | Rameswari
|  |  | Test Flowmodel to flow type assignment | 2 | 20/01/2017 | 20/01/2017 |  |  | Rameswari
Rameswari
4 | As a user I should be able to define and assign procedure to Flow model | 13 | Create page for "Assign FlowModelFlowProcedureDetermination" | 4 | 2017-09-01 | 2017-09-01 |  |  | Vrinda
|  |  | Create controller "FlowprocedureManagedBean" | 8 | 2017-09-01 | 2017-10-01 |  |  | Vrinda
|  |  | Create exceptions for "Flow Procedure" | 3 | 2017-10-01 | 2017-10-01 |  |  | Vrinda
|  |  | Create service interface "FlowprocedureService" | 8 | 2017-10-01 | 2017-11-01 |  |  | Vrinda
|  |  | Create service "DefaultFlowprocedureService" | 8 | 2017-11-01 | 2017-12-01 |  |  | Vrinda
|  |  | Create domain entity Flowprocedure" | 4 | 2017-12-01 | 13/01/2017 |  |  | Vrinda
|  |  | Test Flowprocedue to flow model assignment | 4 | 13/01/2017 | 13/01/2017 |  |  | Vrinda
Vrinda
5 | As a user I should be able to define and assign step to Flow procedure | 8 | Create page for "Assign FlowProcedureFlowstepDetermination" | 2 | 13/01/2017 | 16/01/2017 |  |  | Vrinda
|  |  | Create controller "FlowstepManagedBean" | 4 | 16/01/2017 | 16/01/2017 |  |  | Vrinda
|  |  | Create exceptions for "Flow step" | 2 | 16/01/2017 | 16/01/2017 |  |  | Vrinda
|  |  | Create service interface "FlowstepService" | 5 | 16/01/2017 | 17/01/2017 |  |  | Vrinda
|  |  | Create service "DefaultFlowstepService" | 5 | 17/01/2017 | 17/01/2017 |  |  | Vrinda
|  |  | Create domain entity Flowstep" | 2 | 17/01/2017 | 17/01/2017 |  |  | Vrinda
|  |  | Test FlowStep to flow procedure assignment | 4 | 18/01/2017 | 18/01/2017 |  |  | Vrinda
Vrinda
6 | As a user I should be able to design the flow field group | 5 | Create page for "Create Flowfieldgroup" | 1 | 18/01/2017 | 18/01/2017 |  |  | Vrinda
|  |  | Create page for "Edit Flowfieldgroup" | 0.5 | 18/01/2017 | 18/01/2017 |  |  | Vrinda
|  |  | Create page for "Display Flowfieldgroup" | 0.5 | 18/01/2017 | 18/01/2017 |  |  | Vrinda
|  |  | Create page for "Copy Flowfieldgroup" | 1 | 18/01/2017 | 18/01/2017 |  |  | Vrinda
|  |  | Create page for "Maintain Flowfieldgroup" | 1 | 18/01/2017 | 18/01/2017 |  |  | Vrinda
|  |  | Create page for "FlowfieldgroupList " | 3 | 19/01/2017 | 19/01/2017 |  |  | Vrinda
|  |  | Create controller "FlowfieldgroupManagedBean" | 3 | 19/01/2017 | 19/01/2017 |  |  | Vrinda
|  |  | Create exceptions for "Flowfieldgroup" | 1 | 19/01/2017 | 19/01/2017 |  |  | Vrinda
|  |  | Create service interface "FlowfieldgroupService" | 1 | 19/01/2017 | 19/01/2017 |  |  | Vrinda
|  |  | Create service "DefaultFlowfieldgroupService" | 2 | 20/01/2017 | 20/01/2017 |  |  | Vrinda
|  |  | Create domain entity Flowfieldgroup" | 2 | 27/01/2018 | 27/01/2018 |  |  | Vrinda
|  |  | Test Flowfieldgroup | 2 | 27/01/2019 | 27/01/2019 |  |  | Vrinda
7 | As a user I should be able to design the flow field control screen layout | 8 | Create page for "create FlowfieldcontrolDetermination" | 2 | 2017-09-01 | 2017-09-01 |  |  | zhao
|  |  | Create controller "FlowfieldcontrolManagedBean" | 4 | 2017-09-01 | 2017-09-01 |  |  | zhao
|  |  | Create exceptions for "Flowfieldcontrol" | 2 | 2017-10-01 | 2017-10-01 |  |  | zhao
|  |  | Create service interface "FlowfieldcontrolService" | 5 | 2017-10-01 | 2017-10-01 |  |  | zhao
|  |  | Create service "DefaultFlowfieldcontrolService" | 5 | 2017-10-01 | 2017-11-01 |  |  | zhao
|  |  | Create domain entity Flowfieldcontrol" | 2 | 2017-11-01 | 2017-11-01 |  |  | zhao
|  |  | Test screen layout for flow field control | 4 | 2017-11-01 | 2017-11-01 |  |  | zhao
8 | As a user I should be able to configure flow approver. | 13 | Create page for "actorgroupDetermination" | 2 | 2017-11-01 | 2017-12-01 |  |  | zhao
|  |  | Create controller actorgroupdeterminationManagedBean" | 3 | 2017-12-01 | 2017-12-01 |  |  | zhao
|  |  | Create exceptions for "actorgroupdetermination" | 1 | 2017-12-01 | 2017-12-01 |  |  | zhao
|  |  | Create service interface "actorgroupdeterminationService" | 1 | 2017-12-01 | 2017-12-01 |  |  | zhao
|  |  | Create service "DefaultactorgroupdeterminationService" | 1 | 2017-12-01 | 2017-12-01 |  |  | zhao
|  |  | Create domain entity actorgroupdetermination" | 1 | 2017-12-01 | 2017-12-01 |  |  | zhao
|  |  | Create page for "actorgroupDeterminationList" | 8 | 13/01/2017 | 13/01/2017 |  |  | zhao
|  |  | Create controller actorgroupdeterminationListManagedBean" | 1 | 16/01/2017 | 16/01/2017 |  |  | zhao
|  |  | Create exceptions for "actorgroupdeterminationList" | 8 | 16/01/2017 | 17/01/2017 |  |  | zhao
|  |  | Create service interface "actorgroupdeterminationListService" | 8 | 17/01/2017 | 18/01/2017 |  |  | zhao
|  |  | Create service "DefaultactorgroupdeterminationListService" | 1 | 18/01/2017 | 18/01/2017 |  |  | zhao
|  |  | Create domain entity actorgroupdeterminationList" | 4 | 18/01/2017 | 18/01/2017 |  |  | zhao
|  |  | Test message determination logic | [5 empty] | zhao
9 | As a user I should be able to create a incident request | 5 | Select a flow type from a flow type list | 5 | 18/01/2017 | 19/01/2017 |  |  | zhao
|  |  | Select a flow model from flow model list | 3 | 19/01/2017 | 19/01/2017 |  |  | zhao
|  |  | View the list of procedure for the selected model | 2 | 19/01/2017 | 19/01/2017 |  |  | zhao
|  |  | enter details of the incident | 3 | 20/01/2017 | 20/01/2017 |  |  | zhao
|  |  | Incident should be created | 2 | 20/01/2017 | 20/01/2017 |  |  | zhao
zhao
10 | AS a service desk manager I should be able to create actor groups | 13 | Create page for "Create Actorgroup" | 2 | 2017-09-01 | 2017-09-01 |  |  | Vignesh
|  |  | Create page for "Edit Actorgroup" | 3 | 2017-09-01 | 2017-09-01 |  |  | Vignesh
|  |  | Create page for "Display Actorgroup" | 1 | 2017-09-01 | 2017-09-01 |  |  | Vignesh
|  |  | Create page for "Copy Actorgroup" | 1 | 2017-09-01 | 2017-09-01 |  |  | Vignesh
|  |  | Create page for "Maintain Actorgroup" | 1 | 2017-09-01 | 2017-09-01 |  |  | Vignesh
|  |  | Create page for "ActorgroupList " | 1 | 2017-10-01 | 2017-10-01 |  |  | Vignesh
|  |  | Create controller "ActorgroupManagedBean" | 8 | 2017-10-01 | 2017-11-01 |  |  | Vignesh
|  |  | Create exceptions for "Actorgroup" | 1 | 2017-11-01 | 2017-11-01 |  |  | Vignesh
|  |  | Create service interface "ActorgroupService" | 8 | 2017-12-01 | 2017-12-01 |  |  | Vignesh
|  |  | Create service "DefaultActorgroupService" | 8 | 13/01/2017 | 13/01/2017 |  |  | Vignesh
|  |  | Create domain entityActorgroup" | 1 | 16/01/2017 | 16/01/2017 |  |  | Vignesh
|  |  | Test Actorgroup | 4 | 16/01/2017 | 16/01/2017 |  |  | Vignesh
11 | AS a service desk manager I should be able to assign actors to a actor group | 8 | Create page for "Assign actorActorgroupAssignment" | 2 | 16/01/2017 | 16/01/2017 |  |  | Vignesh
|  |  | Create controller "actorActorgroupAssignmentManagedBean" | 4 | 16/01/2017 | 17/01/2017 |  |  | Vignesh
|  |  | Create exceptions for "actorActorgroupAssignment" | 2 | 17/01/2017 | 17/01/2017 |  |  | Vignesh
|  |  | Create service interface "actorActorgroupAssignmentService" | 5 | 17/01/2017 | 18/01/2017 |  |  | Vignesh
|  |  | Create service "DefaultactorActorgroupAssignmentService" | 5 | 18/01/2017 | 18/01/2017 |  |  | Vignesh
|  |  | Create domain entity actorActorgroupAssignment" | 2 | 19/01/2017 | 19/01/2017 |  |  | Vignesh
|  |  | Test actor to actor group assignment | 4 | 19/01/2017 | 19/01/2017 |  |  | Vignesh
Vignesh
12 | AS a service desk manager I should be able to assign users to actors | 5 | Create page for "Create Actor" | 1 | 19/01/2017 | 19/01/2017 |  |  | Vignesh
|  |  | Create page for "Edit Actor" | 0.5 | 19/01/2017 | 19/01/2017 |  |  | Vignesh
|  |  | Create page for "Display Actor" | 0.5 | 19/01/2017 | 19/01/2017 |  |  | Vignesh
|  |  | Create page for "Copy Actor" | 1 | 20/01/2017 | 20/01/2017 |  |  | Vignesh
|  |  | Create page for "Maintain Actorgroup" | 1 | 20/01/2017 | 20/01/2017 |  |  | Vignesh
|  |  | Create page for "ActorList " | 1 | 20/01/2017 | 20/01/2017 |  |  | Vignesh
|  |  | Create controller "ActorgroupManagedBean" | 1 | 20/01/2017 | 20/01/2017 |  |  | Vignesh
|  |  | Create exceptions for "Actor" | 1 | 20/01/2017 | 20/01/2017 |  |  | Vignesh
|  |  | Create service interface "ActorService" | 1 | 20/01/2017 | 20/01/2017 |  |  | Vignesh
|  |  | Create service "DefaultActorgroupService" | 0.5 | 20/01/2017 | 20/01/2017 |  |  | Vignesh
|  |  | Create domain entityActor" | 0.5 | 20/01/2017 | 20/01/2017 |  |  | Vignesh
|  |  | Test Actor | 2 | 20/01/2017 | 20/01/2017 |  |  | Vignesh
Total No of Working day in Sprint 2 = Days
No if of Hours per day = 8 Hr
No of Resource = 4
Total No of Man Hour for sprint 1= 10*8*4 = 320
Effort per person for Sprint Planning and retrospective =2 day = 8Hr
Total effort for Sprint Planning and Retrospective = 8*4 * 2= 64 Hr
Requirement gathering , Userstories and sprint backlog 3 day = 3*4*8 = 96
Analysis modeling = 2*4*8 = 64
Design modeling= 2*4*8 = 64
Effort per person for Stand up meeting, Work Division and issuse resolution = 1 hr/day
Effort per Person for the sprint = 16 hr
Effort for the team = 16*5 = 80 Hr
Effective Working hour = 640 - (320) = 320
Total Story points allocated in sprint 2 = 104
As per Instant Edge standards 1 Story point = 3Hr
so hours per point = 312 Hr

## Sprint Burndown
SPRINT 2 BURNDOWN
| Days | Planned Hours Burndown | Actual Hours burndown | Dates
| 0 | 320 |  | 16/12/2016
| 1 | 288 |  | 19/12/2016
| 2 | 256 |  | 20/12/2016
| 3 | 224 |  | 21/12/2016
| 4 | 192 |  | 22/12/2016
| 5 | 160 |  | 23/12/2016
| 6 | 128 |  | 27/12/2016
| 7 | 96 |  | 28/12/2016
| 8 | 64 |  | 29/12/2016
| 9 | 32 |  | 30/12/2016
| 10 | 0
SPRINT 3 BURNDOWN
| Days | Planned Hours Burndown | Actual Hours burndown | Dates
| 0 | 320 |  | 2017-09-01
| 1 | 288 |  | 2017-10-01
| 2 | 256 |  | 2017-11-01
| 3 | 224 |  | 2017-12-01
| 4 | 192 |  | 13/1/2017
| 5 | 160 |  | 16/1/2017
| 6 | 128 |  | 17/1/2017
| 7 | 96 |  | 18/1/2017
| 8 | 64 |  | 19/1/2017
| 9 | 32 |  | 20/1/2017
| 10 | 0 |  | 23/1/2017
| 11 | 0 |  | 24/1/2017
| 12 | 0 |  | 25/1/2017
| 13 | 0 |  | 26/1/2017
| 14 | 0 |  | 27/1/2017
| 15 | 0 |  | 28/1/2017