## Sheet1
SL NO | User Story | Story Point | Task | No of Hours | Planned start Date | Planned End date | Actual start Date | Actual End date | Resource
| As a User I should be able to Maintain,Copy,Create,Display,Edit Configurationitem | 5 | Create page for "Create Configurationitem" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Rameswari
|  |  | Create page for "Edit Configurationitem" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Rameswari
|  |  | Create page for "Display Configurationitem" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Rameswari
|  |  | Create page for "Copy Configurationitem" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Rameswari
|  |  | Create page for "Maintain Configurationitem" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Rameswari
|  |  | Create page for "List Configurationitem" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Rameswari
|  |  | Create controller "ConfigurationitemManagedBean" | 2 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Rameswari
|  |  | Create exceptions for "Configurationitem" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Rameswari
|  |  | Create service interface "ConfigurationitemService" | 2 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Rameswari
|  |  | Create service "DefaultConfigurationitemService" | 1 | 20/09/2016 | 23/09/2016 | 20/09/2016 | 23/09/2016 | Rameswari
|  |  | Create domain entity "Configurationitem" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Rameswari
|  |  | Test Configurationitem | 6 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | Rameswari
| As a User I should be able to Maintain,Copy,Create,Display,Edit Configurationitemtype | 5 | Create page for "Create Configurationitemtype" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Rameswari
|  |  | Create page for "Edit Configurationitemtype" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Rameswari
|  |  | Create page for "Display Configurationitemtype" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Rameswari
|  |  | Create page for "Copy Configurationitemtype" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Rameswari
|  |  | Create page for "Maintain Configurationitemtype" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Rameswari
|  |  | Create page for "List Configurationitemtype" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Rameswari
|  |  | Create controller "ConfigurationitemtypeManagedBean" | 2 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Rameswari
|  |  | Create exceptions for "Configurationitemtype" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Rameswari
|  |  | Create service interface "ConfigurationitemtypeService" | 2 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Rameswari
|  |  | Create service "DefaultConfigurationitemtypeService" | 1 | 23/09/2016 | 27/09/2016 | 23/09/2016 | 27/09/2016 | Rameswari
|  |  | Create domain entity "Configurationitemtype" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Rameswari
|  |  | Test Configurationitemtype | 6 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | Rameswari
| As a User I should be able to Maintain,Copy,Create,Display,Edit Configurationitemclass | 5 | Create page for "Create Configurationitemclass" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Rameswari
|  |  | Create page for "Edit Configurationitemclass" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Rameswari
|  |  | Create page for "Display Configurationitemclass" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Rameswari
|  |  | Create page for "Copy Configurationitemclass" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Rameswari
|  |  | Create page for "Maintain Configurationitemclass" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Rameswari
|  |  | Create page for "List Configurationitemclass" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Rameswari
|  |  | Create controller "ConfigurationitemclassManagedBean" | 2 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Rameswari
|  |  | Create exceptions for "Configurationitemclass" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Rameswari
|  |  | Create service interface "ConfigurationitemclassService" | 2 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Rameswari
|  |  | Create service "DefaultConfigurationitemclassService" | 1 | 27/09/2016 | 30/09/2016 | 27/09/2016 | 30/09/2016 | Rameswari
|  |  | Create domain entity "Configurationitemclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Rameswari
|  |  | Test Configurationitemclass | 6 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Rameswari
| As a User I should be able to Maintain,Copy,Create,Display,Edit Configurationitemstatus | 5 | Create page for "Create Configurationitemstatus" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Rameswari
|  |  | Create page for "Edit Configurationitemstatus" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Rameswari
|  |  | Create page for "Display Configurationitemstatus" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Rameswari
|  |  | Create page for "Copy Configurationitemstatus" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Rameswari
|  |  | Create page for "Maintain Configurationitemstatus" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Rameswari
|  |  | Create page for "List Configurationitemstatus" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Rameswari
|  |  | Create controller "ConfigurationitemstatusManagedBean" | 2 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Rameswari
|  |  | Create exceptions for "Configurationitemstatus" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Rameswari
|  |  | Create service interface "ConfigurationitemstatusService" | 2 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Rameswari
|  |  | Create service "DefaultConfigurationitemstatusService" | 1 | 30/09/2016 | 2016-04-10 | 30/09/2016 | 2016-04-10 | Rameswari
|  |  | Create domain entity "Configurationitemstatus" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Rameswari
|  |  | Test Configurationitemstatus | 6 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Rameswari
| As a User I should be able to Maintain,Copy,Create,Display,Edit Configurationitemrepository | 5 | Create page for "Create Configurationitemrepository" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Rameswari
|  |  | Create page for "Edit Configurationitemrepository" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Rameswari
|  |  | Create page for "Display Configurationitemrepository" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Rameswari
|  |  | Create page for "Copy Configurationitemrepository" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Rameswari
|  |  | Create page for "Maintain Configurationitemrepository" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Rameswari
|  |  | Create page for "List Configurationitemrepository" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Rameswari
|  |  | Create controller "ConfigurationitemrepositoryManagedBean" | 2 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Rameswari
|  |  | Create exceptions for "Configurationitemrepository" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Rameswari
|  |  | Create service interface "ConfigurationitemrepositoryService" | 2 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Rameswari
|  |  | Create service "DefaultConfigurationitemrepositoryService" | 1 | 2016-04-10 | 2016-07-10 | 2016-04-10 | 2016-07-10 | Rameswari
|  |  | Create domain entity "Configurationitemrepository" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Rameswari
|  |  | Test Configurationitemrepository | 6 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | Rameswari
| As a User I should be able to Maintain,Copy,Create,Display,Edit Configurationitemcategory | 5 | Create page for "Create Configurationitemcategory" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Rameswari
|  |  | Create page for "Edit Configurationitemcategory" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Rameswari
|  |  | Create page for "Display Configurationitemcategory" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Rameswari
|  |  | Create page for "Copy Configurationitemcategory" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Rameswari
|  |  | Create page for "Maintain Configurationitemcategory" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Rameswari
|  |  | Create page for "List Configurationitemcategory" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Rameswari
|  |  | Create controller "ConfigurationitemcategoryManagedBean" | 2 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Rameswari
|  |  | Create exceptions for "Configurationitemcategory" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Rameswari
|  |  | Create service interface "ConfigurationitemcategoryService" | 2 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Rameswari
|  |  | Create service "DefaultConfigurationitemcategoryService" | 1 | 2016-07-10 | 2016-11-10 | 2016-07-10 | 2016-11-10 | Rameswari
|  |  | Create domain entity "Configurationitemcategory" | 0.5 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | Rameswari
|  |  | Test Configurationitemcategory | 6 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | Rameswari
| As a User I should be able to Maintain,Copy,Create,Display,Edit Contract | 5 | Create page for "Create contract" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vignesh
|  |  | Create page for "Edit contract" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vignesh
|  |  | Create page for "Display contract" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vignesh
|  |  | Create page for "Copy contract" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vignesh
|  |  | Create page for "Maintain contract" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vignesh
|  |  | Create page for "List contract" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vignesh
|  |  | Create controller "contractManagedBean" | 2 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vignesh
|  |  | Create exceptions for "contract" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vignesh
|  |  | Create service interface "contractService" | 2 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vignesh
|  |  | Create service "DefaultcontractService" | 1 | 20/09/2016 | 23/09/2016 | 20/09/2016 | 23/09/2016 | Vignesh
|  |  | Create domain entity "contract" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vignesh
|  |  | Test contract | 6 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | Vignesh
| As a User I should be able to Maintain,Copy,Create,Display,Edit Contractcatalogue | 5 | Create page for "Create contractcatalogue" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vignesh
|  |  | Create page for "Edit contractcatalogue" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vignesh
|  |  | Create page for "Display contractcatalogue" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vignesh
|  |  | Create page for "Copy contractcatalogue" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vignesh
|  |  | Create page for "Maintain contractcatalogue" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vignesh
|  |  | Create page for "List contractcatalogue" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vignesh
|  |  | Create controller "contractcatalogueManagedBean" | 2 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vignesh
|  |  | Create exceptions for "contractcatalogue" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vignesh
|  |  | Create service interface "contractcatalogueService" | 2 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vignesh
|  |  | Create service "DefaultcontractcatalogueService" | 1 | 23/09/2016 | 27/09/2016 | 23/09/2016 | 27/09/2016 | Vignesh
|  |  | Create domain entity "contractcatalogue" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vignesh
|  |  | Test contractcatalogue | 6 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | Vignesh
| As a User I should be able to Maintain,Copy,Create,Display,Edit Contractcategory | 5 | Create page for "Create contractcategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vignesh
|  |  | Create page for "Edit contractcategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vignesh
|  |  | Create page for "Display contractcategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vignesh
|  |  | Create page for "Copy contractcategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vignesh
|  |  | Create page for "Maintain contractcategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vignesh
|  |  | Create page for "List contractcategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vignesh
|  |  | Create controller "contractcategoryManagedBean" | 2 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vignesh
|  |  | Create exceptions for "contractcategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vignesh
|  |  | Create service interface "contractcategoryService" | 2 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vignesh
|  |  | Create service "DefaultcontractcategoryService" | 1 | 27/09/2016 | 30/09/2016 | 27/09/2016 | 30/09/2016 | Vignesh
|  |  | Create domain entity "contractcategory" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vignesh
|  |  | Test contractcategory | 6 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Vignesh
| As a User I should be able to Maintain,Copy,Create,Display,Edit Contractclass | 5 | Create page for "Create contractclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vignesh
|  |  | Create page for "Edit contractclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vignesh
|  |  | Create page for "Display contractclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vignesh
|  |  | Create page for "Copy contractclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vignesh
|  |  | Create page for "Maintain contractclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vignesh
|  |  | Create page for "List contractclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vignesh
|  |  | Create controller "contractclassManagedBean" | 2 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vignesh
|  |  | Create exceptions for "contractclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vignesh
|  |  | Create service interface "contractclassService" | 2 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vignesh
|  |  | Create service "DefaultcontractclassService" | 1 | 30/09/2016 | 2016-04-10 | 30/09/2016 | 2016-04-10 | Vignesh
|  |  | Create domain entity "contractclass" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vignesh
|  |  | Test contractclass | 6 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Vignesh
| As a User I should be able to Maintain,Copy,Create,Display,Edit Contractrepository | 5 | Create page for "Create contractrepository" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vignesh
|  |  | Create page for "Edit contractrepository" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vignesh
|  |  | Create page for "Display contractrepository" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vignesh
|  |  | Create page for "Copy contractrepository" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vignesh
|  |  | Create page for "Maintain contractrepository" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vignesh
|  |  | Create page for "List contractrepository" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vignesh
|  |  | Create controller "contractrepositoryManagedBean" | 2 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vignesh
|  |  | Create exceptions for "contractrepository" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vignesh
|  |  | Create service interface "contractrepositoryService" | 2 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vignesh
|  |  | Create service "DefaultcontractrepositoryService" | 1 | 2016-04-10 | 2016-07-10 | 2016-04-10 | 2016-07-10 | Vignesh
|  |  | Create domain entity "contractrepository" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vignesh
|  |  | Test contractrepository | 6 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | Vignesh
| As a User I should be able to Maintain,Copy,Create,Display,Edit Contracttype | 5 | Create page for "Create contracttype" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vignesh
|  |  | Create page for "Edit contracttype" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vignesh
|  |  | Create page for "Display contracttype" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vignesh
|  |  | Create page for "Copy contracttype" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vignesh
|  |  | Create page for "Maintain contracttype" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vignesh
|  |  | Create page for "List contracttype" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vignesh
|  |  | Create controller "contracttypeManagedBean" | 2 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vignesh
|  |  | Create exceptions for "contracttype" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vignesh
|  |  | Create service interface "contracttypeService" | 2 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vignesh
|  |  | Create service "DefaultcontracttypeService" | 1 | 2016-07-10 | 2016-11-10 | 2016-07-10 | 2016-11-10 | Vignesh
|  |  | Create domain entity "contracttype" | 0.5 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | Vignesh
|  |  | Test contracttype | 6 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | Vignesh
| As a User I should be able to Maintain,Copy,Create,Display,Edit Service | 5 | Create page for "Create service" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vrinda
|  |  | Create page for "Edit service" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vrinda
|  |  | Create page for "Display service" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vrinda
|  |  | Create page for "Copy service" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vrinda
|  |  | Create page for "Maintain service" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vrinda
|  |  | Create page for "List service" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vrinda
|  |  | Create controller "serviceManagedBean" | 2 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vrinda
|  |  | Create exceptions for "service" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vrinda
|  |  | Create service interface "serviceService" | 2 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Vrinda
|  |  | Create service "DefaultserviceService" | 1 | 20/09/2016 | 23/09/2016 | 20/09/2016 | 23/09/2016 | Vrinda
|  |  | Create domain entity "service" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vrinda
|  |  | Test service | 6 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | Vrinda
| As a User I should be able to Maintain,Copy,Create,Display,Edit Servicecatalogue | 5 | Create page for "Create servicecatalogue" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vrinda
|  |  | Create page for "Edit servicecatalogue" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vrinda
|  |  | Create page for "Display servicecatalogue" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vrinda
|  |  | Create page for "Copy servicecatalogue" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vrinda
|  |  | Create page for "Maintain servicecatalogue" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vrinda
|  |  | Create page for "List servicecatalogue" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vrinda
|  |  | Create controller "servicecatalogueManagedBean" | 2 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vrinda
|  |  | Create exceptions for "servicecatalogue" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vrinda
|  |  | Create service interface "servicecatalogueservice" | 2 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Vrinda
|  |  | Create service "Defaultservicecatalogueservice" | 1 | 23/09/2016 | 27/09/2016 | 23/09/2016 | 27/09/2016 | Vrinda
|  |  | Create domain entity "servicecatalogue" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vrinda
|  |  | Test servicecatalogue | 6 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | Vrinda
| As a User I should be able to Maintain,Copy,Create,Display,Edit Servicecataloguecategory | 5 | Create page for "Create servicecataloguecategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vrinda
|  |  | Create page for "Edit servicecataloguecategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vrinda
|  |  | Create page for "Display servicecataloguecategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vrinda
|  |  | Create page for "Copy servicecataloguecategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vrinda
|  |  | Create page for "Maintain servicecataloguecategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vrinda
|  |  | Create page for "List servicecataloguecategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vrinda
|  |  | Create controller "servicecataloguecategoryManagedBean" | 2 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vrinda
|  |  | Create exceptions for "servicecataloguecategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vrinda
|  |  | Create service interface "servicecataloguecategory" | 2 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Vrinda
|  |  | Create service "Defaultservicecataloguecategory" | 1 | 27/09/2016 | 30/09/2016 | 27/09/2016 | 30/09/2016 | Vrinda
|  |  | Create domain entity "servicecataloguecategory" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vrinda
|  |  | Test servicecataloguecategory | 6 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Vrinda
| As a User I should be able to Maintain,Copy,Create,Display,Edit Servicecatalogueclass | 5 | Create page for "Create servicecatalogueclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vrinda
|  |  | Create page for "Edit servicecatalogueclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vrinda
|  |  | Create page for "Display servicecatalogueclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vrinda
|  |  | Create page for "Copy servicecatalogueclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vrinda
|  |  | Create page for "Maintain servicecatalogueclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vrinda
|  |  | Create page for "List servicecatalogueclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vrinda
|  |  | Create controller "servicecatalogueclassManagedBean" | 2 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vrinda
|  |  | Create exceptions for "servicecatalogueclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vrinda
|  |  | Create service interface "servicecatalogueclassService" | 2 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Vrinda
|  |  | Create service "DefaultservicecatalogueclassService" | 1 | 30/09/2016 | 2016-04-10 | 30/09/2016 | 2016-04-10 | Vrinda
|  |  | Create domain entity "servicecatalogueclass" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vrinda
|  |  | Test servicecatalogueclass | 6 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Vrinda
| As a User I should be able to Maintain,Copy,Create,Display,Edit Servicecataloguetype | 5 | Create page for "Create servicecataloguetype" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vrinda
|  |  | Create page for "Edit servicecataloguetype" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vrinda
|  |  | Create page for "Display servicecataloguetype" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vrinda
|  |  | Create page for "Copy servicecataloguetype" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vrinda
|  |  | Create page for "Maintain servicecataloguetype" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vrinda
|  |  | Create page for "List servicecataloguetype" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vrinda
|  |  | Create controller "servicecataloguetypeManagedBean" | 2 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vrinda
|  |  | Create exceptions for "servicecataloguetype" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vrinda
|  |  | Create service interface "servicecataloguetypeService" | 2 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Vrinda
|  |  | Create service "DefaultservicecataloguetypeService" | 1 | 2016-04-10 | 2016-07-10 | 2016-04-10 | 2016-07-10 | Vrinda
|  |  | Create domain entity "servicecataloguetype" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vrinda
|  |  | Test servicecataloguetype | 6 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | Vrinda
| As a User I should be able to Maintain,Copy,Create,Display,Edit Servicecategory | 5 | Create page for "Create servicecategory" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vrinda
|  |  | Create page for "Edit servicecategory" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vrinda
|  |  | Create page for "Display servicecategory" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vrinda
|  |  | Create page for "Copy servicecategory" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vrinda
|  |  | Create page for "Maintain servicecategory" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vrinda
|  |  | Create page for "List servicecategory" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vrinda
|  |  | Create controller "servicecategoryManagedBean" | 2 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vrinda
|  |  | Create exceptions for "servicecategory" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vrinda
|  |  | Create service interface "servicecategoryService" | 2 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Vrinda
|  |  | Create service "DefaultservicecategoryService" | 1 | 2016-07-10 | 2016-11-10 | 2016-07-10 | 2016-11-10 | Vrinda
|  |  | Create domain entity "servicecategory" | 0.5 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | Vrinda
|  |  | Test servicecategory | 6 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | Vrinda
| As a User I should be able to Maintain,Copy,Create,Display,Edit Serviceclass | 5 | Create page for "Create serviceclass" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Keerti
|  |  | Create page for "Edit serviceclass" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Keerti
|  |  | Create page for "Display serviceclass" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Keerti
|  |  | Create page for "Copy serviceclass" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Keerti
|  |  | Create page for "Maintain serviceclass" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Keerti
|  |  | Create page for "List serviceclass" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Keerti
|  |  | Create controller "serviceclassManagedBean" | 2 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Keerti
|  |  | Create exceptions for "serviceclass" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Keerti
|  |  | Create service interface "serviceclassService" | 2 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Keerti
|  |  | Create service "DefaultserviceclassService" | 1 | 20/09/2016 | 23/09/2016 | 20/09/2016 | 23/09/2016 | Keerti
|  |  | Create domain entity "serviceclass" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Keerti
|  |  | Test serviceclass | 6 |  |  | 25/10/2016 | 25/10/2016 | Vignesh
| As a User I should be able to Maintain,Copy,Create,Display,Edit Serviceportfolio | 5 | Create page for "Create service portfolio" | 0.5 | 23/09/2016 | 23/09/2016 | 30/09/2016 | 30/09/2016 | Keerti
|  |  | Create page for "Edit service portfolio" | 0.5 | 23/09/2016 | 23/09/2016 | 30/09/2016 | 30/09/2016 | Keerti
|  |  | Create page for "Display service portfolio" | 0.5 | 23/09/2016 | 23/09/2016 | 30/09/2016 | 30/09/2016 | Keerti
|  |  | Create page for "Copy Service Portfolio" | 0.5 | 23/09/2016 | 23/09/2016 | 30/09/2016 | 30/09/2016 | Keerti
|  |  | Create page for "Maintain Service Portfolio" | 0.5 | 23/09/2016 | 23/09/2016 | 30/09/2016 | 30/09/2016 | Keerti
|  |  | Create page for "List Service Portfolio" | 0.5 | 23/09/2016 | 23/09/2016 | 30/09/2016 | 30/09/2016 | Keerti
|  |  | Create controller "ServiceportfolioManagedBean" | 2 | 23/09/2016 | 23/09/2016 | 30/09/2016 | 30/09/2016 | Keerti
|  |  | Create exceptions for "Serviceportfolio" | 0.5 | 23/09/2016 | 23/09/2016 | 30/09/2016 | 30/09/2016 | Keerti
|  |  | Create service interface "ServiceportfolioService" | 2 | 23/09/2016 | 23/09/2016 | 30/09/2016 | 30/09/2016 | Keerti
|  |  | Create service "DefaultServiceportfolioService" | 1 | 23/09/2016 | 27/09/2016 | 30/09/2016 | 30/09/2016 | Keerti
|  |  | Create domain entity "Serviceportfolio" | 0.5 | 27/09/2016 | 27/09/2016 | 30/09/2016 | 30/09/2016 | Keerti
|  |  | Test Service Portfolio | 6 | 25/10/2016 | 25/10/2016 | 25/10/2016 | 25/10/2016 | Vignesh
| As a User I should be able to Maintain,Copy,Create,Display,Edit Serviceportfoliocategory | 5 | Create page for "Create service portfoliocategory" | 0.5 | 27/09/2016 | 27/09/2016 | 2016-04-10 | 2016-04-10 | Keerti
|  |  | Create page for "Edit service portfoliocategory" | 0.5 | 27/09/2016 | 27/09/2016 | 2016-04-10 | 2016-04-10 | Keerti
|  |  | Create page for "Display service portfoliocategory" | 0.5 | 27/09/2016 | 27/09/2016 | 2016-04-10 | 2016-04-10 | Keerti
|  |  | Create page for "Copy Service Portfoliocategory" | 0.5 | 27/09/2016 | 27/09/2016 | 2016-04-10 | 2016-04-10 | Keerti
|  |  | Create page for "Maintain Service Portfoliocategory" | 0.5 | 27/09/2016 | 27/09/2016 | 2016-04-10 | 2016-04-10 | Keerti
|  |  | Create page for "List Service Portfoliocategory" | 0.5 | 27/09/2016 | 27/09/2016 | 2016-04-10 | 2016-04-10 | Keerti
|  |  | Create controller "ServiceportfoliocategoryManagedBean" | 2 | 27/09/2016 | 27/09/2016 | 2016-04-10 | 2016-04-10 | Keerti
|  |  | Create exceptions for "Serviceportfoliocategory" | 0.5 | 27/09/2016 | 27/09/2016 | 2016-04-10 | 2016-04-10 | Keerti
|  |  | Create service interface "ServiceportfoliocategoryService" | 2 | 27/09/2016 | 27/09/2016 | 2016-04-10 | 2016-04-10 | Keerti
|  |  | Create service "DefaultServiceportfoliocategoryService" | 1 | 27/09/2016 | 30/09/2016 | 2016-04-10 | 2016-04-10 | Keerti
|  |  | Create domain entity "Serviceportfoliocategory" | 0.5 | 30/09/2016 | 30/09/2016 | 2016-04-10 | 2016-04-10 | Keerti
|  |  | Test Service Portfoliocategory | 6 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Zhao
| As a User I should be able to Maintain,Copy,Create,Display,Edit Serviceportfolioclass | 5 | Create page for "Create service portfolioclass" | 0.5 | 30/09/2016 | 30/09/2016 | 19/10/2016 | 19/10/2016 | Rameswari
|  |  | Create page for "Edit service portfolioclass" | 0.5 | 30/09/2016 | 30/09/2016 | 19/10/2016 | 19/10/2016 | Rameswari
|  |  | Create page for "Display service portfolioclass" | 0.5 | 30/09/2016 | 30/09/2016 | 19/10/2016 | 19/10/2016 | Rameswari
|  |  | Create page for "Copy Service Portfolioclass" | 0.5 | 30/09/2016 | 30/09/2016 | 19/10/2016 | 19/10/2016 | Rameswari
|  |  | Create page for "Maintain Service Portfolioclass" | 0.5 | 30/09/2016 | 30/09/2016 | 19/10/2016 | 19/10/2016 | Rameswari
|  |  | Create page for "List Service Portfolioclass" | 0.5 | 30/09/2016 | 30/09/2016 | 19/10/2016 | 19/10/2016 | Rameswari
|  |  | Create controller "ServiceportfolioclassManagedBean" | 2 | 30/09/2016 | 30/09/2016 | 19/10/2016 | 19/10/2016 | Rameswari
|  |  | Create exceptions for "Serviceportfolioclass" | 0.5 | 30/09/2016 | 30/09/2016 | 19/10/2016 | 19/10/2016 | Rameswari
|  |  | Create service interface "ServiceportfolioclassService" | 2 | 30/09/2016 | 30/09/2016 | 19/10/2016 | 19/10/2016 | Rameswari
|  |  | Create service "DefaultServiceportfolioclassService" | 1 | 30/09/2016 | 2016-04-10 | 19/10/2016 | 19/10/2016 | Rameswari
|  |  | Create domain entity "Serviceportfolioclass" | 0.5 | 2016-04-10 | 2016-04-10 | 19/10/2016 | 19/10/2016 | Rameswari
|  |  | Test Service Portfolioclass | 6 | 19/10/2016 | 25/10/2016 | 19/10/2016 | 25/10/2016 | Rameswari
| As a User I should be able to Maintain,Copy,Create,Display,Edit Serviceportfoliodimensions | 5 | Create page for "Create service portfoliodimensions" | 0.5 | 2016-04-10 | 2016-04-10 | 19/10/2016 | 19/10/2016 | Vrinda
|  |  | Create page for "Edit service portfoliodimensions" | 0.5 | 2016-04-10 | 2016-04-10 | 19/10/2016 | 19/10/2016 | Vrinda
|  |  | Create page for "Display service portfoliodimensions" | 0.5 | 2016-04-10 | 2016-04-10 | 19/10/2016 | 19/10/2016 | Vrinda
|  |  | Create page for "Copy Service Portfoliodimensions" | 0.5 | 2016-04-10 | 2016-04-10 | 19/10/2016 | 19/10/2016 | Vrinda
|  |  | Create page for "Maintain Service Portfoliodimensions" | 0.5 | 2016-04-10 | 2016-04-10 | 19/10/2016 | 19/10/2016 | Vrinda
|  |  | Create page for "List Service Portfoliodimensions" | 0.5 | 2016-04-10 | 2016-04-10 | 19/10/2016 | 19/10/2016 | Vrinda
|  |  | Create controller "ServiceportfoliodimensionsManagedBean" | 2 | 2016-04-10 | 2016-04-10 | 19/10/2016 | 19/10/2016 | Vrinda
|  |  | Create exceptions for "Serviceportfoliodimensions" | 0.5 | 2016-04-10 | 2016-04-10 | 19/10/2016 | 19/10/2016 | Vrinda
|  |  | Create service interface "ServiceportfoliodimensionsService" | 2 | 2016-04-10 | 2016-04-10 | 19/10/2016 | 19/10/2016 | Vrinda
|  |  | Create service "DefaultServiceportfoliodimensionsService" | 1 | 2016-04-10 | 2016-07-10 | 19/10/2016 | 19/10/2016 | Vrinda
|  |  | Create domain entity "Serviceportfoliodimensions" | 0.5 | 2016-07-10 | 2016-07-10 | 19/10/2016 | 19/10/2016 | Vrinda
|  |  | Test Service Portfoliodimensions | 6 | 19/10/2016 | 25/10/2016 | 19/10/2016 | 25/10/2016 | Vrinda
| As a User I should be able to Maintain,Copy,Create,Display,Edit Serviceportfoliodimensionstype | 5 | Create page for "Create service portfoliodimensionstype" | 0.5 | 2016-07-10 | 2016-07-10 | 19/10/2016 | 19/10/2016 | Vignesh
|  |  | Create page for "Edit service portfoliodimensionstype" | 0.5 | 2016-07-10 | 2016-07-10 | 19/10/2016 | 19/10/2016 | Vignesh
|  |  | Create page for "Display service portfoliodimensionstype" | 0.5 | 2016-07-10 | 2016-07-10 | 19/10/2016 | 19/10/2016 | Vignesh
|  |  | Create page for "Copy Service Portfoliodimensionstype" | 0.5 | 2016-07-10 | 2016-07-10 | 19/10/2016 | 19/10/2016 | Vignesh
|  |  | Create page for "Maintain Service Portfoliodimensionstype" | 0.5 | 2016-07-10 | 2016-07-10 | 19/10/2016 | 19/10/2016 | Vignesh
|  |  | Create page for "List Service Portfoliodimensionstype" | 0.5 | 2016-07-10 | 2016-07-10 | 19/10/2016 | 19/10/2016 | Vignesh
|  |  | Create controller "ServiceportfoliodimensionstypeManagedBean" | 2 | 2016-07-10 | 2016-07-10 | 19/10/2016 | 19/10/2016 | Vignesh
|  |  | Create exceptions for "Serviceportfoliodimensionstype" | 0.5 | 2016-07-10 | 2016-07-10 | 19/10/2016 | 19/10/2016 | Vignesh
|  |  | Create service interface "ServiceportfoliodimensionstypeService" | 2 | 2016-07-10 | 2016-07-10 | 19/10/2016 | 19/10/2016 | Vignesh
|  |  | Create service "DefaultServiceportfoliodimensionstypeService" | 1 | 2016-07-10 | 2016-11-10 | 19/10/2016 | 19/10/2016 | Vignesh
|  |  | Create domain entity "Serviceportfoliodimensionstype" | 0.5 | 2016-11-10 | 2016-11-10 | 19/10/2016 | 19/10/2016 | Vignesh
|  |  | Test Service Portfoliodimensionstype | 6 | 19/10/2016 | 25/10/2016 | 19/10/2016 | 25/10/2016 | Vignesh
| As a User I should be able to Maintain,Copy,Create,Display,Edit Serviceportfoliogroup | 5 | Create page for "Create service portfoliogroup" | 0.5 | 2016-12-10 | 2016-12-10 | 25/10/2016 | 25/10/2016 | Rameswari
|  |  | Create page for "Edit service portfoliogroup" | 0.5 | 2016-12-10 | 2016-12-10 | 25/10/2016 | 25/10/2016 | Rameswari
|  |  | Create page for "Display service portfoliogroup" | 0.5 | 2016-12-10 | 2016-12-10 | 25/10/2016 | 25/10/2016 | Rameswari
|  |  | Create page for "Copy Service Portfoliogroup" | 0.5 | 2016-12-10 | 2016-12-10 | 25/10/2016 | 25/10/2016 | Rameswari
|  |  | Create page for "Maintain Service Portfoliogroup" | 0.5 | 2016-12-10 | 2016-12-10 | 25/10/2016 | 25/10/2016 | Rameswari
|  |  | Create page for "List Service Portfoliogroup" | 0.5 | 2016-12-10 | 2016-12-10 | 25/10/2016 | 25/10/2016 | Rameswari
|  |  | Create controller "ServiceportfoliogroupManagedBean" | 2 | 2016-12-10 | 2016-12-10 | 25/10/2016 | 25/10/2016 | Rameswari
|  |  | Create exceptions for "Serviceportfoliogroup" | 0.5 | 2016-12-10 | 2016-12-10 | 25/10/2016 | 25/10/2016 | Rameswari
|  |  | Create service interface "ServiceportfoliogroupService" | 2 | 2016-12-10 | 2016-12-10 | 25/10/2016 | 25/10/2016 | Vrinda
|  |  | Create service "DefaultServiceportfoliogroupService" | 1 | 2016-12-10 | 2016-12-10 | 25/10/2016 | 25/10/2016 | Vrinda
|  |  | Create domain entity "Serviceportfoliogroup" | 0.5 | 2016-12-10 | 2016-12-10 | 25/10/2016 | 25/10/2016 | Vrinda
|  |  | Test Service Portfoliogroup | 6 | 18/10/2016 | 18/10/2016 | 25/10/2016 | 25/10/2016 | Vrinda
| As a User I should be able to Maintain,Copy,Create,Display,Edit Serviceportfoliotype | 5 | Create page for "Create service portfoliotype" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Zhao
|  |  | Create page for "Edit service portfoliotype" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Zhao
|  |  | Create page for "Display service portfoliotype" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Zhao
|  |  | Create page for "Copy Service Portfoliotype" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Zhao
|  |  | Create page for "Maintain Service Portfoliotype" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Zhao
|  |  | Create page for "List Service Portfoliotype" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Zhao
|  |  | Create controller "ServiceportfoliotypeManagedBean" | 2 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Zhao
|  |  | Create exceptions for "Serviceportfoliotype" | 0.5 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Zhao
|  |  | Create service interface "ServiceportfoliotypeService" | 2 | 20/09/2016 | 20/09/2016 | 20/09/2016 | 20/09/2016 | Zhao
|  |  | Create service "DefaultServiceportfoliotypeService" | 1 | 20/09/2016 | 23/09/2016 | 20/09/2016 | 23/09/2016 | Zhao
|  |  | Create domain entity "Serviceportfoliotype" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Zhao
|  |  | Test Service Portfoliotype | 6 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | Zhao
| As a User I should be able to Maintain,Copy,Create,Display,Edit Servicequality | 5 | Create page for "Create service quality" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Zhao
|  |  | Create page for "Edit service quality" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Zhao
|  |  | Create page for "Display service quality" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Zhao
|  |  | Create page for "Copy Service quality" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Zhao
|  |  | Create page for "Maintain Service quality" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Zhao
|  |  | Create page for "List Service quality" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Zhao
|  |  | Create controller "ServicequalityManagedBean" | 2 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Zhao
|  |  | Create exceptions for "Servicequality" | 0.5 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Zhao
|  |  | Create service interface "ServicequalityService" | 2 | 23/09/2016 | 23/09/2016 | 23/09/2016 | 23/09/2016 | Zhao
|  |  | Create service "DefaultServicequalityService" | 1 | 23/09/2016 | 27/09/2016 | 23/09/2016 | 27/09/2016 | Zhao
|  |  | Create domain entity "Servicequality" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Zhao
|  |  | Test Service quality | 6 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | Zhao
| As a User I should be able to Maintain,Copy,Create,Display,Edit Servicequalitycategory | 5 | Create page for "Create service qualitycategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Zhao
|  |  | Create page for "Edit service qualitycategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Zhao
|  |  | Create page for "Display service qualitycategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Zhao
|  |  | Create page for "Copy Service qualitycategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Zhao
|  |  | Create page for "Maintain Service qualitycategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Zhao
|  |  | Create page for "List Service qualitycategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Zhao
|  |  | Create controller "ServicequalitycategoryManagedBean" | 2 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Zhao
|  |  | Create exceptions for "Servicequalitycategory" | 0.5 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Zhao
|  |  | Create service interface "ServicequalitycategoryService" | 2 | 27/09/2016 | 27/09/2016 | 27/09/2016 | 27/09/2016 | Zhao
|  |  | Create service "DefaultServicequalitycategoryService" | 1 | 27/09/2016 | 30/09/2016 | 27/09/2016 | 30/09/2016 | Zhao
|  |  | Create domain entity "Servicequalitycategory" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Zhao
|  |  | Test Service qualitycategory | 6 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Zhao
| As a User I should be able to Maintain,Copy,Create,Display,Edit Servicequalityclass | 5 | Create page for "Create service qualityclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Zhao
|  |  | Create page for "Edit service qualityclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Zhao
|  |  | Create page for "Display service qualityclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Zhao
|  |  | Create page for "Copy Service qualityclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Zhao
|  |  | Create page for "Maintain Service qualityclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Zhao
|  |  | Create page for "List Service qualityclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Zhao
|  |  | Create controller "ServicequalityclassManagedBean" | 2 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Zhao
|  |  | Create exceptions for "Servicequalityclass" | 0.5 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Zhao
|  |  | Create service interface "ServicequalityclassService" | 2 | 30/09/2016 | 30/09/2016 | 30/09/2016 | 30/09/2016 | Zhao
|  |  | Create service "DefaultServicequalityclassService" | 1 | 30/09/2016 | 2016-04-10 | 30/09/2016 | 2016-04-10 | Zhao
|  |  | Create domain entity "Servicequalityclass" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Zhao
|  |  | Test Service qualityclass | 6 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | Zhao
| As a User I should be able to Maintain,Copy,Create,Display,Edit Servicequalitytype | 5 | Create page for "Create service qualitytype" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Zhao
|  |  | Create page for "Edit service qualitytype" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Zhao
|  |  | Create page for "Display service qualitytype" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Zhao
|  |  | Create page for "Copy Service qualitytype" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Zhao
|  |  | Create page for "Maintain Service qualitytype" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Zhao
|  |  | Create page for "List Service qualitytype" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Zhao
|  |  | Create controller "ServicequalitytypeManagedBean" | 2 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Zhao
|  |  | Create exceptions for "Servicequalitytype" | 0.5 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Zhao
|  |  | Create service interface "ServicequalitytypeService" | 2 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | Zhao
|  |  | Create service "DefaultServicequalitytypeService" | 1 | 2016-04-10 | 2016-07-10 | 2016-04-10 | 2016-07-10 | Zhao
|  |  | Create domain entity "Servicequalitytype" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Zhao
|  |  | Test Service qualitytype | 6 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | Zhao
| As a User I should be able to Maintain,Copy,Create,Display,Edit Servicerepository | 5 | Create page for "Create service repository" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Zhao
|  |  | Create page for "Edit service repository" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Zhao
|  |  | Create page for "Display service repository" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Zhao
|  |  | Create page for "Copy Service repository" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Zhao
|  |  | Create page for "Maintain Service repository" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Zhao
|  |  | Create page for "List Service repository" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Zhao
|  |  | Create controller "ServicerepositoryManagedBean" | 2 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Zhao
|  |  | Create exceptions for "Servicerepository" | 0.5 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Zhao
|  |  | Create service interface "ServicerepositoryService" | 2 | 2016-07-10 | 2016-07-10 | 2016-07-10 | 2016-07-10 | Zhao
|  |  | Create service "DefaultServicerepositoryService" | 1 | 2016-07-10 | 2016-11-10 | 2016-07-10 | 2016-11-10 | Zhao
|  |  | Create domain entity "Servicerepository" | 0.5 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | Zhao
|  |  | Test Service repository | 6 | 2016-02-11 | 2016-02-11 | 2016-02-11 | 2016-02-11 | Zhao
| As a User I should be able to Maintain,Copy,Create,Display,Edit Servicestatus | 5 | Create page for "Create service status" | 0.5 | 25/10/2016 | 25/10/2016 | 25/10/2016 | 25/10/2016 | Zhao
|  |  | Create page for "Edit service status" | 0.5 | 25/10/2016 | 25/10/2016 | 25/10/2016 | 25/10/2016 | Zhao
|  |  | Create page for "Display service status" | 0.5 | 25/10/2016 | 25/10/2016 | 25/10/2016 | 25/10/2016 | Zhao
|  |  | Create page for "Copy Service status" | 0.5 | 25/10/2016 | 25/10/2016 | 25/10/2016 | 25/10/2016 | Zhao
|  |  | Create page for "Maintain Service status" | 0.5 | 25/10/2016 | 25/10/2016 | 25/10/2016 | 25/10/2016 | Zhao
|  |  | Create page for "List Service status" | 0.5 | 25/10/2016 | 25/10/2016 | 25/10/2016 | 25/10/2016 | Zhao
|  |  | Create controller "ServicestatusManagedBean" | 2 | 25/10/2016 | 25/10/2016 | 25/10/2016 | 25/10/2016 | Zhao
|  |  | Create exceptions for "Servicestatus" | 0.5 | 25/10/2016 | 25/10/2016 | 25/10/2016 | 25/10/2016 | Zhao
|  |  | Create service interface "ServicestatusService" | 2 | 25/10/2016 | 25/10/2016 | 25/10/2016 | 25/10/2016 | Zhao
|  |  | Create service "DefaultServicestatusService" | 1 | 25/10/2016 | 25/10/2016 | 25/10/2016 | 25/10/2016 | Zhao
|  |  | Create domain entity "Servicestatus" | 0.5 | 25/10/2016 | 25/10/2016 | 25/10/2016 | 25/10/2016 | Zhao
|  |  | Test Service status | 6 | 25/10/2016 | 25/10/2016 | 25/10/2016 | 25/10/2016 | Zhao
| As a User I should be able to Maintain,Copy,Create,Display,Edit Servicetype | 5 | Create page for "Create service type" | 0.5 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Zhao
|  |  | Create page for "Edit service type" | 0.5 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Zhao
|  |  | Create page for "Display service type" | 0.5 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Zhao
|  |  | Create page for "Copy Service type" | 0.5 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Zhao
|  |  | Create page for "Maintain Service type" | 0.5 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Zhao
|  |  | Create page for "List Service type" | 0.5 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Zhao
|  |  | Create controller "ServicetypeManagedBean" | 2 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Zhao
|  |  | Create exceptions for "Servicetype" | 0.5 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Zhao
|  |  | Create service interface "ServicetypeService" | 2 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Zhao
|  |  | Create service "DefaultServicetypeService" | 1 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Zhao
|  |  | Create domain entity "Servicetype" | 0.5 | 26/10/2016 | 26/10/2016 | 26/10/2016 | 26/10/2016 | Zhao
|  |  | Test Service type | 6 | 2016-02-11 | 2016-02-11 | 2016-02-11 | 2016-02-11 | Zhao
| As a Service Portfolio Owner I should be able to view the manage operations tab under my work in the login landing page | 1 | Add manage operations tab under my work in the login landing page | 3 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2016-04-11 | Zhao
| As a Service Portfolio Owner I should be able to view the option of service portfolio when I click manage operations tab. | 1 | Add option of service portfolio when to manage operations tab. | 3 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2016-04-11 | Zhao
| As a Service Portfolio Owner I should be able to click on service portfolio and land on the portfolio list page. | 1 | connect service portfolio to the portfolio list page. | 3 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2016-04-11 | Zhao
| As a Service Portfolio Owner I should be able to view all my portfolio on the portfolio list page | 1 | Populate the list of portfolio for the current user on the portfolio list page | 3 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2016-04-11 | Zhao
| As a Service Portfolio Owner I should be able to filter the portfolio based on portfolio type | 1 | Enable filter the portfolio based on portfolio type | 3 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2016-04-11 | Rameswari
| As a Service Portfolio Owner I should be able to filter the portfolio based on portfolio dimension type | 1 | Enable filter the portfolio based on portfolio dimension type | 3 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2016-04-11 | Rameswari
| As a Service Portfolio Owner I should be able to filter the portfolio with respect to dimensions. | 3 | Enable filter the portfolio with respect to dimensions. | 9 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2016-04-11 | Rameswari
| As a Service Portfolio Owner I should be able to filter the portfolio based on multiple portfolio type | 1 | Enable filter the portfolio based on multiple portfolio type | 3 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2016-04-11 | Rameswari
| As a Service Portfolio Owner I should be able to filter the portfolio based on multiple dimension type | 3 | Enable filter the portfolio based on multiple dimension type | 9 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2016-04-11 | Vignesh
| As a Service Portfolio Owner I should be able to filter the portfolio based on multiple dimension | 1 | Enable filter the portfolio based on multiple dimension | 3 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2016-04-11 | Vrinda
| As a Service Portfolio Owner I should be able to search the portfolio by keyword or name from the search bar | 1 | Enable search the portfolio by keyword or name from the search bar | 3 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2016-04-11 | Vrinda
| As a Service Portfolio Owner I should be navigated to the dashboard page once I click on selected portfolio | 1 | connect the portfolio to the respective dashboard page on click | 3 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2016-04-11 | Vrinda
| As a Service Portfolio Owner I should be able to view all combinations of dimension and dimension type | 1 | Ensure vsibility of all combinations of dimension and dimension type | 3 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2016-04-11 | Vrinda
| As a Service Portfolio Owner I should be able to revert any selection made inside the filter and update the lists. | 1 | enable revert of any selection made inside the filter and update the lists. | 3 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | Vignesh
| As a Service Portfolio Owner I should be able to sort the portfolio list by different attributes of a portfolio | 1 | Enable sorting the portfolio list by different attributes of a portfolio | 3 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | Vignesh
| As a Service Portfolio Owner I should be directed to dashboard page once I select a portfolio | 1 | connect the service dashboard page from its corresonding portfolio | 3 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | Vignesh
| As a Service Portfolio Owner I should be able to get the overview of the portfolio on the dashboard | 1 | create an overview of the portfolio on the dashboard | 3 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | Vignesh
| As a Service Portfolio Owner I should be able to click on Service attributes to view their details | 1 | Make the Service attributes to view their details | 3 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | zhao
| As a Service Portfolio Owner I should be able to view the list of services in a service portfolio | 1 | populate a list of services in a service portfolio | 3 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | zhao
| As a Service Portfolio Owner I should be able to filter the services based on different service attributes | 1 | Enable filter the services based on different service attributes | 3 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | zhao
| As a Service Portfolio Owner I should be able to filter the services by service type | 1 | Enable filter the services by service type | 3 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | zhao
| As a Service Portfolio Owner I should be able to filter the service by service type | 1 | Enable filter the service by service type | 3 | 2016-09-11 | 2016-09-11 | 2016-09-11 | 2016-09-11 | Rameswari
| As a Service Portfolio Owner I should be able to search for services by search keyword | 1 | Enable search for services by search keyword | 3 | 2016-09-11 | 2016-09-11 | 2016-09-11 | 2016-09-11 | Vrinda
| As a Service Portfolio Owner I should be able to view the updated lists after the filters are applied | 1 | Enable refresh lists after the filters are applied | 3 | 2016-09-11 | 2016-09-11 | 2016-09-11 | 2016-09-11 | Vignesh
| As a Service Portfolio Owner I should be able to click on service to get the service overview | 1 | link the service to get the service overview | 3 | 2016-09-11 | 2016-09-11 | 2016-09-11 | 2016-09-11 | Zhao