## Sprint 2
SL NO | User Story | Story Point | Task | No of Hours | Planned start Date | Planned End date | Actual start Date | Actual End date | Resource
3 | As a user I should be able to configure FlowType of an incident |  | Create page for "Create Flowtype" | [5 empty] | Vrinda
|  |  | Create page for "Edit Flowtype" | [5 empty] | Vrinda
|  |  | Create page for "Display Flowtype" | [5 empty] | Vrinda
|  |  | Create page for "Copy Flowtype" | [5 empty] | Vrinda
|  |  | Create page for "Maintain Flowtype" | [5 empty] | Vrinda
|  |  | Create page for "FlowtypeList " | [5 empty] | Vrinda
|  |  | Create controller "FlowtypeManagedBean" | [5 empty] | Vrinda
|  |  | Create exceptions for "Flowtype" | [5 empty] | Vrinda
|  |  | Create service interface "FlowtypeService" | [5 empty] | Vrinda
|  |  | Create service "DefaultFlowtypeService" | [5 empty] | Vrinda
|  |  | Create domain entity Flowtype" | [5 empty] | Vrinda
|  |  | Test Flowtype | [5 empty] | Vrinda
4 | As a user I chould be able to configure FlowModel of an incident |  | Create page for "Create FlowModel" | [5 empty] | Zhao
|  |  | Create page for "Edit Flowmodel" | [5 empty] | Zhao
|  |  | Create page for "Display Flowmodel" | [5 empty] | Zhao
|  |  | Create page for "Copy Flowmodel" | [5 empty] | Zhao
|  |  | Create page for "Maintain FlowModel" | [5 empty] | Zhao
|  |  | Create page for "FlowmodelList " | [5 empty] | Zhao
|  |  | Create controller "FlowmodelManagedBean" | [5 empty] | Zhao
|  |  | Create exceptions for "Flowmodel" | [5 empty] | Zhao
|  |  | Create service interface "FlowmodelService" | [5 empty] | Zhao
|  |  | Create service "DefaultFlowmodelService" | [5 empty] | Zhao
|  |  | Create domain entity Flowmodel" | [5 empty] | Zhao
|  |  | Test Flowmodel | [5 empty] | Zhao
5 | As a user I should be able to assign Flow model to Flow Type |  | Create page for "FlowModel FlowType assignment"
Create controller "FlowmodelFlowTypeManagedBean"
Create exceptions for "FlowmodelFlowtype"
Create service interface "FlowmodelFlowtypeService"
Create service "DefaultFlowmodelFlowtypeService"
Create domain entity FlowmodelFlowtype"
Test Flowmodel to flow type assignment
6 | As a user I should be able to define and assign procedure to Flow model |  | Create page for "Assign FlowModelFlowProcedureDetermination"
Create controller "FlowprocedureManagedBean"
Create exceptions for "Flow Procedure"
Create service interface "FlowprocedureService"
Create service "DefaultFlowprocedureService"
Create domain entity Flowprocedure"
Test Flowprocedue to flow model assignment
7 | As a user I should be able to define and assign step to Flow procedure |  | Create page for "Assign FlowProcedureFlowstepDetermination"
Create controller "FlowstepManagedBean"
Create exceptions for "Flow step"
Create service interface "FlowstepService"
Create service "DefaultFlowstepService"
Create domain entity Flowstep"
Test FlowStep to flow procedure assignment
8 | As a user I should be able to design the flow field group |  | Create page for "Create Flowfieldgroup"
Create page for "Edit Flowfieldgroup"
Create page for "Display Flowfieldgroup"
Create page for "Copy Flowfieldgroup"
Create page for "Maintain Flowfieldgroup"
Create page for "FlowfieldgroupList "
Create controller "FlowfieldgroupManagedBean"
Create exceptions for "Flowfieldgroup"
Create service interface "FlowfieldgroupService"
Create service "DefaultFlowfieldgroupService"
Create domain entity Flowfieldgroup"
Test Flowfieldgroup
9 | As a user I should be able to design the flow field control screen layout |  | Create page for "create FlowfieldcontrolDetermination"
Create controller "FlowfieldcontrolManagedBean"
Create exceptions for "Flowfieldcontrol"
Create service interface "FlowfieldcontrolService"
Create service "DefaultFlowfieldcontrolService"
Create domain entity Flowfieldcontrol"
Test screen layout for flow field control
10 | As a user I should be able to configure flow approver. |  | Create page for "actorgroupDetermination"
Create controller actorgroupdeterminationManagedBean"
Create exceptions for "actorgroupdetermination"
Create service interface "actorgroupdeterminationService"
Create service "DefaultactorgroupdeterminationService"
Create domain entity actorgroupdetermination"
Create page for "actorgroupDeterminationList"
Create controller actorgroupdeterminationListManagedBean"
Create exceptions for "actorgroupdeterminationList"
Create service interface "actorgroupdeterminationListService"
Create service "DefaultactorgroupdeterminationListService"
Create domain entity actorgroupdeterminationList"
Test message determination logic
11 | As a user I should be able to create a incident request |  | Select a flow type from a flow type list
Select a flow model from flow model list
View the list of procedure for the selected model
enter details of the incident
Incident should be created
12 | AS a service desk manager I should be able to create actor groups |  | Create page for "Create Actorgroup"
Create page for "Edit Actorgroup"
Create page for "Display Actorgroup"
Create page for "Copy Actorgroup"
Create page for "Maintain Actorgroup"
Create page for "ActorgroupList "
Create controller "ActorgroupManagedBean"
Create exceptions for "Actorgroup"
Create service interface "ActorgroupService"
Create service "DefaultActorgroupService"
Create domain entityActorgroup"
Test Actorgroup
13 | AS a service desk manager I should be able to assign actors to a actor group |  | Create page for "Assign actorActorgroupAssignment"
Create controller "actorActorgroupAssignmentManagedBean"
Create exceptions for "actorActorgroupAssignment"
Create service interface "actorActorgroupAssignmentService"
Create service "DefaultactorActorgroupAssignmentService"
Create domain entity actorActorgroupAssignment"
Test actor to actor group assignment
14 | AS a service desk manager I should be able to assign users to actors |  | Create page for "Create Actor"
Create page for "Edit Actor"
Create page for "Display Actor"
Create page for "Copy Actor"
Create page for "Maintain Actorgroup"
Create page for "ActorList "
Create controller "ActorgroupManagedBean"
Create exceptions for "Actor"
Create service interface "ActorService"
Create service "DefaultActorgroupService"
Create domain entityActor"
Test Actor

## Sprint 3
SL NO | User Story | Story Point | Task | No of Hours | Planned start Date | Planned End date | Actual start Date | Actual End date | Planned Resource
15 | As a User, I want to access the platform on my mobile so that I can get updates instantly | 13 |  |  | 2016-12-12 | 2016-12-12 |  |  | Vignesh
|  |  | Create an cross platform mobile application in Microsoft Xamarin(android) . |  | 13/12/2016 | 15/12/2016 |  |  | Zhao
|  |  | Create an cross platform mobile application in Microsoft Xamarin (ios). |  | 14/12/2016 | 16/12/2016 |  |  | Vignesh
|  |  | Create a Xamarin project with Android App, |  | 16/12/2016 | 20/12/2016 |  |  | Zhao
|  |  | Create a Xamarin project with , iOS App and a Shared Code base |  | 19/12/2016 | 21/12/2016 |  |  | Vignesh
|  |  | Create Mobile Activity to display login page in android |  | 21/12/2016 | 21/12/2016 |  |  | Zhao
|  |  | Create Mobile Activity to display list of inbox items in android |  | 21/12/2016 | 21/12/2016 |  |  | Zhao
|  |  | Create Mobile Activity to display details of notifications in android |  | 21/12/2016 | 21/12/2016 |  |  | Zhao
|  |  | Create Storyboard item to display login page in iOS |  | 22/12/2016 | 22/12/2016 |  |  | Vignesh
|  |  | Create Storyboard item to display list of inbox items in iOS |  | 22/12/2016 | 22/12/2016 |  |  | Vignesh
|  |  | Create Storyboard item to display details of notifications in iOS |  | 22/12/2016 | 22/12/2016 |  |  | Vignesh
16 | As a User, I should be able to login to Instant Edge platform on my mobile application | 13 | Implement JWT token based authentication in server side. |  | 22/12/2016 | 22/12/2016 |  |  | Zhao
|  |  | Create a rest end point to authenticate users and generate JWT |  | 22/12/2016 | 22/12/2016 |  |  | Zhao
|  |  | Develop mobile UI to get user credentials |  | 23/12/2016 | 23/12/2016 |  |  | Zhao
|  |  | Communicate with instant edge server and obtain JWT |  | 23/12/2016 | 23/12/2016 |  |  | Zhao
|  |  | Create rest end point to obtain FCM token from devices |  | 23/12/2016 | 23/12/2016 |  |  | Vignesh
|  |  | Register the FCM token with users list of devices |  | 23/12/2016 | 28/12/2016 |  |  | Vignesh
|  |  | Refresh FCM token in fixed intervals |  | 27/12/2016 | 28/12/2016 |  |  | Zhao
|  |  | Send a IE generated Device token back to devices |  | 28/12/2016 | 28/12/2016 |  |  | Vignesh
|  |  | From the device send local device token to FCM and obtain FCM token |  | 29/12/2016 | 29/12/2016 |  |  | Zhao
|  |  | Send the FCM token to server to register for Push Notifications |  | 30/12/2016 | 30/12/2016 |  |  | Zhao
|  |  | Obtain Server generated Device token fro deregistration in the future |  | 29/12/2016 | 29/12/2016 |  |  | Vignesh
17 | As a User, I want to receive a notification when I receive a new item in my unified box, so that I can handle it on time. | 8 | Create a new FCM message |  | 23/12/2016 | 23/12/2016 |  |  | Rameswari
|  |  | Send FCM message using serverID, generated during FCM account creation |  | 23/12/2016 | 23/12/2016 |  |  | Vrinda
|  |  | Test the iOS Feature |  | 23/12/2016 | 28/12/2016 |  |  | Rameswari
|  |  | Test the Android Feature |  | 23/12/2016 | 28/12/2016 |  |  | Vrinda
18 | As a User, I should be able to view my dashboard when I login to the mobile application | 8 | Create a browser wrapper and set URL as IE dashboard page |  | 29/12/2016 | 29/12/2016 |  |  | Vrinda
|  |  | Create a new session in IE using JWT |  | 29/12/2016 | 29/12/2016 |  |  | Vrinda
|  |  | Build and set cookie for the wrapper |  | 29/12/2016 | 29/12/2016 |  |  | Vrinda
|  |  | Load the URL |  | 29/12/2016 | 29/12/2016 |  |  | Vrinda
19 | As a User I should be able to logout from the mobile application | 5 | Send IE Generated device token to IE Server's logout endpoint |  | 30/12/2016 | 30/12/2016 |  |  | Vrinda
|  |  | Create rest end point to receive logout requests and deregister device token from the users list of devices |  | 29/12/2016 | 29/12/2016 |  |  | Rameswari
|  |  | Clear all user data from device |  | 30/12/2016 | 30/12/2016 |  |  | Rameswari
20 | As a User, I want to click on the notification, so that I can be redirected to my unified inbox | 5 | Redirect to the wrapper when a notification is clicked |  | 30/12/2016 | 30/12/2016 |  |  | Vignesh
|  |  | Investigate mobile cross platform technologies | 4
|  |  | Investigate FCM and APNS configuration. | 4
|  |  | Finalize technology | 4
|  |  | Create FCM account and a project under it | 4
|  |  | Provision an iOS and android app under the project | 4
|  |  | Create provision for a new iOS app in apple developer portal - APNS | 4

## Sheet1
SL NO | User Story | Story Point | Task | No of Hours | Planned start Date | Planned End date | Actual start Date | Actual End date | No of Hours Spent | Resource
1 | As a User, I want to access the platform on my Android mobile so that I can get updates instantly | 13
|  |  | Create an cross platform mobile application in Microsoft Xamarin(android) . | 16 | 16/12/2016 | 19/12/2016 | 16/12/2016 | 19/12/2016 | 16 | Zhao
|  |  | Create a Xamarin project with Android App, | 5 | 20/12/2016 | 20/12/2016 | 20/12/2016 | 20/12/2016 | 5 | Zhao
|  |  | Create Mobile Activity to display login page in android | 5 | 20/12/2016 | 21/12/2016 | 20/12/2016 | 21/12/2016 | 5 | Zhao
|  |  | Create Mobile Activity to display list of inbox items in android | 5 | 21/12/2016 | 21/12/2016 | 21/12/2016 | 22/12/2016 | 5 | Zhao
|  |  | Create Mobile Activity to display details of notifications in android | 8 | 22/12/2016 | 22/12/2016 | 22/12/2016 | 22/12/2016 | 10 | Zhao
2 | As a User, I want to access the platform on my iOS mobile so that I can get updates instantly | 13
|  |  | Create an cross platform mobile application in Microsoft Xamarin (ios). | 16 | 16/12/2016 | 19/12/2016 |  |  | 12 | Vignesh
|  |  | Create a Xamarin project with , iOS App and a Shared Code base | 5 | 20/12/2016 | 20/12/2016 |  |  | 5 | Vignesh
|  |  | Create Storyboard item to display login page in iOS | 5 | 20/12/2016 | 21/12/2016 |  |  | 5 | Vignesh
|  |  | Create Storyboard item to display list of inbox items in iOS | 5 | 21/12/2016 | 21/12/2016 |  |  | 5 | Vignesh
|  |  | Create Storyboard item to display details of notifications in iOS | 8 | 22/12/2016 | 22/12/2016 |  |  | 8 | Vignesh
3 | As a User, I should be able to login to Instant Edge platform on my android mobile application | 5 | Implement JWT token based authentication in server side. | 1 | 22/12/2016 | 22/12/2016 |  |  | 1 | Zhao
|  |  | Create a rest end point to authenticate users and generate JWT | 0.5 | 23/12/2016 | 23/12/2016 |  |  | 1 | Zhao
|  |  | Develop mobile UI to get user credentials | 0.5 | 23/12/2016 | 23/12/2016 |  |  | 1 | Zhao
|  |  | Communicate with instant edge server and obtain JWT | 1 | 23/12/2016 | 23/12/2016 |  |  | 2 | Zhao
|  |  | Create rest end point to obtain FCM token from devices | 1 | 23/12/2016 | 23/12/2016 |  |  | 1 | Zhao
|  |  | Register the FCM token with users list of devices | 5 | 23/12/2016 | 23/12/2016 |  |  | 5 | Zhao
|  |  | Refresh FCM token in fixed intervals | 3 | 27/12/2016 | 27/12/2016 |  |  | 2 | Zhao
|  |  | Send a IE generated Device token back to devices | 1 | 27/12/2016 | 27/12/2016 |  |  | 1 | Zhao
|  |  | From the device send local device token to FCM and obtain FCM token | 1 | 27/12/2016 | 27/12/2016 |  |  | 1 | Zhao
|  |  | Send the FCM token to server to register for Push Notifications | 0.5 | 27/12/2016 | 27/12/2016 |  |  | 1 | Zhao
|  |  | Obtain Server generated Device token fro deregistration in the future | 0.5 | 27/12/2016 | 27/12/2016 |  |  | 1 | Zhao
4 | As a User, I should be able to login to Instant Edge platform on my iOS mobile application | 5 | Implement JWT token based authentication in server side. | 1 | 22/12/2016 | 22/12/2016 |  |  | 0.5 | Vignesh
|  |  | Create a rest end point to authenticate users and generate JWT | 0.5 | 23/12/2016 | 23/12/2016 |  |  | 1 | Vignesh
|  |  | Develop mobile UI to get user credentials | 0.5 | 23/12/2016 | 23/12/2016 |  |  | 0.5 | Vignesh
|  |  | Communicate with instant edge server and obtain JWT | 1 | 23/12/2016 | 23/12/2016 |  |  | 1 | Vignesh
|  |  | Create rest end point to obtain FCM token from devices | 1 | 23/12/2016 | 23/12/2016 |  |  | 1 | Vignesh
|  |  | Register the FCM token with users list of devices | 5 | 23/12/2016 | 23/12/2016 |  |  | 3 | Vignesh
|  |  | Refresh FCM token in fixed intervals | 3 | 27/12/2016 | 27/12/2016 |  |  | 3 | Vignesh
|  |  | Send a IE generated Device token back to devices | 1 | 27/12/2016 | 27/12/2016 |  |  | 1 | Vignesh
|  |  | From the device send local device token to FCM and obtain FCM token | 1 | 27/12/2016 | 27/12/2016 |  |  | 1 | Vignesh
|  |  | Send the FCM token to server to register for Push Notifications | 0.5 | 27/12/2016 | 27/12/2016 |  |  | 0.5 | Vignesh
|  |  | Obtain Server generated Device token fro deregistration in the future | 0.5 | 27/12/2016 | 27/12/2016 |  |  | 0.5 | Vignesh
5 | As a User, I should be able to view my dashboard when I login to the mobile application | 5 | Design the browser wrapper | 3 | 27/12/2016 | 28/12/2016 |  |  | 3 | Zhao
|  |  | Create a browser wrapper and set URL as IE dashboard page | 5 | 28/12/2016 | 28/12/2016 |  |  | 6 | Zhao
|  |  | Create a new session in IE using JWT | 2 | 28/12/2016 | 28/12/2016 |  |  | 3 | Zhao
|  |  | Build and set cookie for the wrapper | 2 | 29/12/2016 | 29/12/2016 |  |  | 3 | Zhao
|  |  | Load the URL | 1 | 29/12/2016 | 29/12/2016 |  |  | 3 | Zhao
|  |  | Test the URL | 2 | 29/12/2016 | 29/12/2016 |  |  | 3 | Zhao
6 | As a User, I want to receive a notification when I receive a new item in my unified box, so that I can handle it on time. | 5 | Create a new FCM message | 5 | 27/12/2016 | 28/12/2016 |  |  | 5 | Vignesh
|  |  | Send FCM message using serverID, generated during FCM account creation | 5 | 28/12/2016 | 28/12/2016 |  |  | 5 | Vignesh
|  |  | Test the iOS Feature | 3 | 28/12/2016 | 29/12/2016 |  |  | 2 | Vignesh
|  |  | Test the Android Feature | 2 | 29/12/2016 | 29/12/2016 |  |  | 2 | Vignesh
7 | As a User I should be able to logout from the mobile application | 3 | Send IE Generated device token to IE Server's logout endpoint | 3 | 29/12/2016 | 29/12/2016 |  |  | 3 | Zhao
|  |  | Create rest end point to receive logout requests and deregister device token from the users list of devices | 2 | 30/12/2016 | 30/12/2016 |  |  | 2 | Zhao
|  |  | Clear all user data from device | 2 | 30/12/2016 | 30/12/2016 |  |  | 2 | Zhao
|  |  | Test logout functionality | 2 | 30/12/2016 | 30/12/2016 |  |  | 1 | Zhao
8 | As a User, I want to click on the notification, so that I can be redirected to my unified inbox | 3 | Design the wrapper functionality | 3 | 29/12/2016 | 29/12/2016 |  |  | 3 | Vignesh
|  |  | Redirect to the wrapper when a notification is clicked | 2 | 30/12/2016 | 30/12/2016 |  |  | 2 | Vignesh
|  |  | Login automatically using JWT | 2 | 30/12/2016 | 30/12/2016 |  |  | 2 | Vignesh
|  |  | Test the wrapper functionality | 2 | 30/12/2016 | 30/12/2016 |  |  | 1 | Vignesh
Story Point
9 | As a User, I want redesign the Actor Group Determination table , so as to avoid too much scrolling in the dialogue | 13 | Designing the UI for Actor Group Determination | 7 | 19/12/2016 | 19/12/2016 |  |  |  | Vrinda
|  |  | Understanding the flaws in the existing system | 6 | 19/12/2016 | 2016-12-20 |  |  |  | Vrinda
|  |  | Minimising use of scrollers | 5 | 2016-12-20 | 2016-12-21 |  |  |  | Vrinda
|  |  | Making efficient use of Tabs | 5 | 2016-12-21 | 2016-12-21 |  |  |  | Vrinda
|  |  | Prototyping page "actorgroupDetermination.xhtml" | 10 | 2016-12-21 | 2016-12-22 |  |  |  | Vrinda
|  |  | Prototyping "actorgroupDeterminationList.xhtml" | 6 | 2016-12-23 | 2016-12-23 |  |  |  | Vrinda
10 | As an Architect, I want to be able to easily maintain the Actor Group Determination (AGD) without scrolling too much | 13 | Create page for "actorgroupDetermination" | 7 | 19/12/2016 | 19/12/2016 |  |  |  | Rameswari
|  |  | Use tabs instead of scroller | 8 | 2016-12-20 | 2016-12-20 |  |  |  | Rameswari
|  |  | Create controller "actorActorgroupAssignmentManagedBean" | 4 | 2016-12-20 | 2016-12-21 |  |  |  | Rameswari
|  |  | Change page "actorgroupDetermination.xhtml" | 9 | 2016-12-21 | 2016-12-22 |  |  |  | Rameswari
|  |  | Create controller actorgroupdeterminationManagedBean" | 8 | 2016-12-22 | 2016-12-23 |  |  |  | Rameswari
|  |  | Test the Actor Group Determination Table | 3 | 2016-12-23 | 2016-12-23 |  |  |  | Rameswari
11 | As a Developer, I should place the edit buttons in such a way that they are consistent throughout the application | 5 | Change the page for "Assign FlowModelFlowProcedureDetermination" | 5 | 2016-12-23 | 2016-12-27 |  |  |  | Vrinda
|  |  | Change the page for "FlowModel FlowType assignment" | 4 | 2016-12-27 | 2016-12-27 |  |  |  | Vrinda
|  |  | Change the page for "Create FlowModel" | 3 | 2016-12-28 | 2016-12-28 |  |  |  | Vrinda
|  |  | Test the Functionality | 3 | 2016-12-28 | 2016-12-28 |  |  |  | Vrinda
12 | As a developer, I should change all the flow type to type and flow model to model | 5 | Change the page for "Create Flowtype" | 5 | 2016-12-23 | 2016-12-24 |  |  |  | Rameswari
|  |  | Change the page for "Create FlowModel" | 4 | 2016-12-27 | 2016-12-27 |  |  |  | Rameswari
|  |  | Change the page for "Assign FlowModelFlowProcedureDetermination" | 3 | 2016-12-28 | 2016-12-28 |  |  |  | Rameswari
|  |  | Change the page for "FlowModel FlowType assignment" | 3 | 2016-12-28 | 2016-12-28 |  |  |  | Rameswari
13 | As a developer, I should be sure that the cancel button works consistently for all the pages | 3 | Changes in page for "Maintain Flowfieldgroup" | 3 | 2016-12-28 | 2016-12-29 |  |  |  | Vrinda
|  |  | Changes in page for "Maintain Actorgroup" | 2 | 2016-12-29 | 2016-12-29 |  |  |  | Vrinda
|  |  | Testing the button in all the pages | 4 | 2016-12-29 | 2016-12-29 |  |  |  | Vrinda
14 | As a developer, I should have some heading for Assignment of Flow Model to Flow Type the flow model list | 3 | Assignment of Flow Step to Flow Procedure | 3 | 2016-12-28 | 2016-12-29 |  |  |  | Rameswari
|  |  | Testing the button in all the pages | 2 | 2016-12-29 | 2016-12-29 |  |  |  | Rameswari
|  |  | Testing the button in all the pages | 4 | 2016-12-29 | 2016-12-29 |  |  |  | Rameswari
15 | As a developer, I should differentiate Message overview, Attachment and message History , so as not to confuse the user | 5 | Changes in Create Incident | 8 | 2016-12-29 | 30/12/2016 |  |  |  | Vrinda
|  |  | Changes in "Create Incident Managed bean" | 3 | 30/12/2016 | 2016-12-31 |  |  |  | Vrinda
|  |  | Changes in "Create Flow Procedure Managed Bean" | 2 | 2016-12-31 | 2016-12-31 |  |  |  | Vrinda
|  |  | Testing the functionality | 2 | 2016-12-31 | 2016-12-31 |  |  |  | Vrinda
16 | As a developer, I want to be sure that the delete button in Assignment of Flow Step to Flow Procedure should delete the Step. | 5 | Assignment of "FlowModel FlowType" | 4 | 2016-12-29 | 30/12/2016 |  |  |  | Rameswari
|  |  | Assign flow procedure to model page. | 4 | 30/12/2016 | 30/12/2016 |  |  |  | Rameswari
|  |  | Changes in page for "Create Flowfieldgroup" | 4 | 30/12/2016 | 2016-12-31 |  |  |  | Rameswari
|  |  | Testing the button in all the pages | 3 | 2016-12-31 | 2016-12-31 |  |  |  | Rameswari

## Sheet2
Days | Planned Hours Burndown | Actual Hours burndown | Dates
0 | 240
1 | 224
2 | 208
3 | 192
4 | 176
5 | 160
6 | 128
7 | 96
8 | 64
9 | 32
10 | 0