## Sheet1
Sprint 0 & Sprint 1
S. No | Review Date | Reviewed by | Doc Name | File Name | Version | Section | Issue Description | Assigned To | Status | Comments
1 | 2016-08-18 | Selvaraju Vignesh | Prototype Study Report | ISS_IE_PSR_1.0.docx | 1.0 | Document Naming convention | Set correct header and footer | Zhao Pengcheng | Closed
2 | 2016-09-06 | Vrinda Gupta | Project Plan | ISS_IE_PP_1.0.docx | 1.0 | Cover Page | File name and reference are different | Rameswari Mohanty | Closed
3 | 2016-09-06 | Zhao Pengcheng | Function point Count | ISS_IE_FPC_1.0.docx | 1.0 | Footer | Set proper version number | Ramewari Mohanty | Closed
4 | 2016-09-06 | Ramewari Mohanty | Quality Plan | ISS_IE_QP_1.0.docx | 1.0 | Document Naming convention | Header and Footer is missing | Vrinda Gupta | Closed
5 | 2016-09-06 | Vrinda Gupta | Skill Matrix | ISS_IE_SM_1.0.xls | 1.0 | Document Naming convention | Document naming convention is not proper | Ramewari Mohanty | Closed
6 | 2016-09-08 | Zhao Pengcheng | UCMS | ISS_IE_UCMS_1.0.docx | 1.0 | Cover Page | File name and reference are different | Selvaraju Vignesh | Closed
7 | 2016-09-08 | Selvaraju Vignesh | Design Model Report | ISS_IE_DMR_1.0.docx | 1.0 | Figure 1 : Architecture Design Overview | The arrow should be bidirection | Zhao Pengcheng | Closed
8 | 2016-09-08 | Rameswari Mohanty | Requirement Traceability Matrix | ISS_IE_RTM_1.0.xls | 1.0 | 2.2.1 Syntax | C#, C++ and Javascripts should follow different coding convention. | Vrinda Gupta | Closed
9 | 2016-09-10 | Vrinda Gupta | URS | ISS_IE_URS_1.0.docx | 1.0 |  | Accept all tracking changes | Selvaraju Vignesh | Closed
10 | 2016-10-08 | Rameswari Mohanty | Test Plan | ISS_IE_UTP_1.0.docx | 1.0 | Cover Page | Correct the format of cover page | Vrinda Gupta | Closed
11 | 2016-10-08 | Selvaraju Vignesh | Requirement Model Report | ISS_IE_RMR_1.0.docx | 1.0 | Figure 4.1 | Few documents have version part. Remove it | Zhao Pengcheng | Closed
12 | 2016-10-15 | Vrinda Gupta | Configuration Management | ISS_IE_CM_1.0.docx | 1.0 |  | Set proper Filing reference for all the documents | Ramewari Mohanty | Closed
13 | 2016-10-15 | Zhao Pengcheng | Effort Estimation | ISS_IE_EE_1.0.xls | 1.0 | Footer | Set proper version number | Ramewari Mohanty | Closed
14 | 2016-10-23 | Selvaraju Vignesh | High Level Design | ISS_IE_HLD_1.0.docx | 1.0 | Cover Page | Set proper version number | Zhao Pengcheng | Closed
Sprint 2 & Sprint 3
S. No | Review Date | Reviewed by | Doc Name | File Name | Version | Section | Issue Description | Assigned To | Status | Comments
15 | 2016-12-02 | Rameswari Mohanty | URS | ISS_IE_URS_2.0.docx | 2 | Cover Page | Change the Team Members | Selvaraju Vignesh | Closed
16 | 2016-12-02 | Rameswari Mohanty | Test Plan | ISS_IE_TP_2.0 | 2 | Cover Page | Change in Team Members | Vrinda Gupta | Closed
17 | 2016-12-05 | Rameswari Mohanty | Configuration Management Plan | ISS_IE_CM_2.0 | 2 |  | Change in Team Members | Selvaraju Vignesh | Closed
18 | 2016-12-05 | Zhao Pengcheng | Quality Plan | ISS_IE_QP_2.0 | 2 | Cover Page | Change in Scope | Vrinda Gupta | Closed
19 | 2016-12-05 | Rameswari Mohanty | URS | ISS_IE_URS_2.1.docx | 2.1 |  | Change of Scope | Vrinda Gupta | Closed
20 | 2016-01-10 | Rameswari Mohanty | Test Plan | ISS_IE_TP_2.2 | 2.2 | 3.5, 4.5 | Include Manage incident | Vrinda Gupta | Closed
21 | 2016-12-12 | Vrinda Gupta | Project Plan | ISS_IE_PP_1.1.docx | 1.1 | 4,5 | Replan for new available resource | Rameswari Mohanty | Closed
22 | 2016-12-15 | Rameswari Mohanty | Test Plan | ISS_IE_TP_2.1 | 2.1 | 3.4, 4.4 | Including Manage Mobile Integration | Vrinda Gupta | Closed
23 | 2016-12-15 | Zhao Pengcheng | URS | ISS_IE_URS_2.2.docx | 2.2 | 3.1.3 | Requirements for Manage Mobile Integration | Vrinda Gupta | Closed
24 | 2016-12-20 | Vrinda Gupta | Project Plan | ISS_IE_PP_2.docx | 2 |  | Replanning of Project scope | Rameswari Mohanty | Closed
25 | 2016-12-20 | Zhao Pengcheng | URS | ISS_IE_URS_2.3.docx | 2.3 | 3.1.2 | Requirements for Manage Incident | Vrinda Gupta | Closed
26 | 2016-12-23 | Selvaraju Vignesh | URS | ISS_IE_URS_2.4.docx | 2.4 | 3.1.3 | Change in Manage Mobile Integration Requirements | Rameswari Mohanty | Closed
27 | 2017-01-05 | Selvaraju Vignesh | URS | ISS_IE_URS_2.5.docx | 2.5 | 3.1.2 | Change in Manage Incidents Requirements | Vrinda Gupta | Closed
28 | 2017-01-05 | Vrinda Gupta | Project Plan | ISS_IE_PP_2.1.docx | 2.1 |  | Replan Push notification feature | Rameswari Mohanty | Closed
Sprint 4 & Sprint 5
S. No | Review Date | Reviewed by | Doc Name | File Name | Version | Section | Issue Description | Assigned To | Status | Comments
29 | 2017-02-01 | Selvaraju VIgnesh | Requirement Model Report | ISS/IE/RMR/2.0 | 2 |  | Changes in the domain model | Vrinda Gupta | Closed
30 | 2017-03-05 | Zhao Pengcheng | UCRR-D | ISS/IE/UCRR-D/2.0 | 2 |  | Changes in the Routing Incident Diagrams | Rameswari Mohanty | Closed
31 | 2017-03-05 | Selvaraju Vignesh | UCRR-A | ISS/IE/UCRR-A/2.0 | 2 |  | Added Flow routing diagrams | Zhao Pengcheng | Closed