## Cover Page
Risk Register Instant Edge
Document Reference: | ISS/IE/RM.1.1
Project: | Instant Edge
Document Title: | Risk Register
Version: | 1
Date: | 28th August 2016
Author: | Vrinda Gupta

## Update history
Version History Record
Version | Date | Brief description of amendments and affected pages, paragraph | Author
1 | 2016-08-20 | First Issue | Vrinda Gupta
1 | 2016-08-25 | Second Issue | Vrinda Gupta
1 | 2016-08-25 | Third Issue | Vrinda Gupta
1 | 2016-09-09 | Fourth Issue | Vrinda Gupta
1 | 2016-10-12 | Fifth Issue | Vrinda Gupta

## Risk Register
RISK REGISTER
Project Name: |  | Intant Edge
Project Manager: |  | Rameswari Mohanty
Prepared By: |  | Vrinda Gupta
Filing Reference: |  | ISS/IE/MP.1/1
©
Summary |  |  | Description | [5 empty] | Preventative Actions | Contingency Actions | Preventative & Contingency Action Define Date | Contingency Action Trigger Point | Is Active | Occurred
ID | Date Raised | Raised By | Risk Item | Condition | Consequence | Risk Type | Risk Resolution Technique | Priority Rating
1 | 20/08/2016 | Team | Ambiguities in Requirements | We work on this project for Instant Edge. Since it’s a new product and the requirements for this module depends on the success previous module. The previous module will go live with the first in october, so requirements are still ambiguous from client's side. | It is sometimes difficult to define and finalize project requirements as we are not sure of what to keep and what not to. | Customer Risk | Risk Localization | M | All team members to study existing software which provide similar services, and understand what the common requirements for such kind platforms are. | The team members approached ISS teachers and studied different competitor products to gain knowlwdge and take feedbacks . | 2016-09-01 | During the completion of product backlog | N | Y
2 | 2016-08-25 | Team | Lack of technical skills in different programming languages and platforms | Team members have in-depth knowledge in a particular programming language but, not broad based programming experience. | Consequence:It may takes time for the developer to research and understand the new technologies it may lead to risk of project schedule being over run, Increase cost of the project and can introduce more defects in the system due to lack of experience. | Technology Risk | Risk Localization | H | Team requires to gain knowledge by reading books or taking online training on different technologies which they are not comfortable with. Skills matrix have been designed to understand weak areas of team members so, that thay can sharpen their skills. | To seek guidance from programming language experts for technical issues faced like all the members of the team were required to take up ejava course as thier elective, and in the event of failure, in accordance with client and project co-ordinator reduce the scope of the project | 2016-10-19 | Ongoing | N | Y
3 | 2016-08-25 | Team | Lack of domain knowledge | Team members have in-depth knowledge in a particular domain but, not broad based on ITIL Framework. | Consequence:It may takes time for the team to research and understand the new framework it may lead to risk of project schedule being over run, Increase cost of the project and can introduce more defects in the system due to lack of experience. | Technology Risk | Risk Localization | H | Team requires to gain knowledge by reading books or taking online training on different technologies which they are not comfortable with. Skills matrix have been designed to understand weak areas of team members so, that thay can sharpen their skills. | To seek guidance from programming language experts for technical issues faced, and in the event of failure, in accordance with client and project co-ordinator reduce the scope of the project. Lot of book on ITIL best practises were read by the team members. | 2016-10-19 | Ongoing because ITIL framework is too large to understand | N | Y
4 | 2016-09-09 | Team | Team members unable to attend discussions and hand in deliverables on time | Project team members not able to attend the weekly discussions, and/or unable to hand in the tasks assigned to them on time due to what ever reasons. | Delay in project schedule due to fixed resources and schedule. | Management Risk | Risk Transfer | M | Make sure that each member reports to the project manager about his/her travel schedule at least for the next 3 months, so that the PM can plan early and minimize the risk. | Find a backup of the people who travel and reassign his work to someone else in the team. | 2016-10-12 | Whenever a team member becomes uncontactable for a certain period of time | N | Y
5 | 2016-10-12 | Team | Lack of Human Resources | At the mid of sprint 1, one of our techical lead dropped out of the project. Only 4 members remained in the team (FT4). | The team is short-staffed and lack of resources to work on various types of deliverablies for sprint 1 | Resources Risk (Human Resources) | Risk Insurance | H | To emphasize to the team the significance of this project and encourage people to stay. | To divide the work equally among all the remaining Team members and request for reducing the scope if possible. | 2016-10-20 | CLOSED | N | Y
6 | 2016-12-06 | Team | Unclear Requirements for the Mobile Application | Condition: The requirements only stated the need for Push Notifications and the actual functionalities of the mobile app are not stated. Consequence: | It is unclear how the application should look and the extend of platform features that the application should provide. | Customer Risk | Risk Localization | M | All team members to study existing software which provide similar services, and understand what the common requirements for such kind platforms. | Setup more meetings with the client to fully understand the requirements and participate in acceptance test for the mock-ups and/or suggest improvement ideas so that the design and functionalities can be finalized | 2016-12-13 | Sprint planning | N | Y
7 | 2016-12-20 | Team | Lack of technical skills in different programming languages and platforms | After 1 week of learning Xamarin, we decided that we cannot adhere to the project schedule because the learning curve is too steep. | The team decided to built two native apps one for ios and one for Android since we had training in both | Technology Risk | Risk Localization | M | Team is required to gain knowledge by reading books or by taking online courses on Xamarin and C#.NET technologies which they are not comfortable with. Skills matrix have been designed to understand weak areas of team members so, that thay can sharpen their skills. | Since the technologies are not enforced by the client and have never been used before (no need for integration), the technologies could be changed to match the skillset of team (probably native development instead of cross-platform development). | 2016-12-28 | After finalizing Module Scope | N | Y
8 | 2017-01-05 | Team | Change in Requirement | Initially Team sponsors asked us to work on incident management and it was decided to run it as a standalone functionality without having much impact on the existing system | The sponsors want us to merge incident management with change management which might significantly increase required effort and eventually affect the project schedule. | Customer Risk | Risk Localization | H | Reuse the workflow engine for both Incident and change management so that the effort required will be reduced. Spend more time on the integration part and logic modifications. | Put in extra hours to understand the change management with the developer who already worked on it. Allocate some off-hours to understand the existing sequential flow and design the new logic and integration logic for existing components to work with the newly proposed flexible logic. | 2017-01-09 | Sprint planning | N | Y
9 | 2017-02-05 | Team | Requirement of merging change management with iNcident management | Some of the features of change and incident management may not be able to merged together | may be the code needs to be refactored or some of the conflicting features of change and incident management have to be discarded even after development which will result in effort wastage | Customer Risk | Risk isolation | H | Make the features more generic so as to handel both scenario | Team member try to make it clear with regular meetings with sponsor | 2017-02-05 | Sprint planning | N | N
10 | 2017-02-05 | Team | Instant Edge Technical Architect going on long leave | Some of the complex logic needs to be changed in the absence of the technical architect | Due to lack of sufficient knowledge some associated functionality may be hampered | Customer Risk | Risk Localization | M | Take adequate KT from the technical Architect | Team member organized regular meetings with technical architect to get the KT | 2017-02-05 | Sprint planning | N | N
11 | 2017-03-20 | Team | Already Existing Defects in the System | There are some already existing defects in the System which may hamper our code | We need to refactor some part of the existing code if it aaffects our work | Technology Risk | Risk Localization | H | Inform the technical architect to look into the problem so that he can refactor the code prior | Team members had to refactor the code themselves with the help of the product owners as the technical architect was on leave | 2017-03-26 | Sprint planning | N | Y
12 | 2017-03-22 | Team | Fuzzy Requirement | Whenever there is a new requirement, it is unclear to the Team as well as the product owners | Due to lack of sufficient knowledge some associated functionality may be hampered | Customer Risk | Risk Localization | M | Understant the new requirement clearly. Make scenarios and examples to see what is feasible and what is not.(The Pick up Functionality) | The team had to put in extra effort to understand the requirement and explained their findings to the product owners | 2017-03-26 | Sprint planning | N | Y

## Risk Impact and Priority
RISK IMPACT
No. | Risk Item | Impact | [5 empty] | Likelihood
|  | 1 | 2 | 3 | 4 | 5 | Total | 1 | 2 | 3 | 4 | 5 | Total
1. | Ambiguities in Requirements | x | x | x | x | x | 5 |  | x | x |  | x | 3
2. | Lack of technical skills in different programming languages and platforms |  |  | x |  | x | 2 |  |  | x | x | x | 3
3. | Lack of domain knowledge | x |  | x |  | x | 3 |  |  | x | x | x | 3
4. | Team members unable to attend discussions and hand in deliverables on time |  | x | x |  | x | 3 |  |  | x |  | x | 2
5. | Lack of Human Resources | x |  | x |  | x | 3 |  |  | x | x | x | 3
Impact Legend:
1. Reduced functionality: Will this Risk Item significantly reduce the original intended functionality of the product, if it occurs.
2. Increased Cost: Will this Risk item have a high impact on the remainder of the project in terms of cost overrun if it occurs
3. Schedule Slippage: Will the risk create schedule slippage.
4. Quality Cost: Will this risk result in a low quality product which will in turn lead to failure in quality audits, reviews or user acceptance tests
5. Performance: Will this risk result in a low performance product which will not meet user’s expectations?
Likelihood Legend:
1. Novelty: Does risk involve new technology or techniques that have not been used before by the project team
2. Product History: Has this risk item occurred in projects where similar products were constructed?
3. Project Team History: Did the members of the project team encounter this risk item on previous projects?
4. Recognised Authority: Does the available specialist advice perceive this to be a likely risk
5. Expectation: Does the current documentation gives a clear idea/model for overcoming this risk item has been reviewed and approved.

## Prioritized Risks
Prioritized Risks
# | Risk | Impact score | Likelihood score | Total score
1 | Lack of knowledge in frameworks and technologies | 4 | 3 | 7
2 | Lack of knowledge in project domain | 2 | 1 | 3
3 | Complexity of Use cases | 4 | 3 | 7
4 | Team Member hand in deliverables on time | 3 | 3 | 6
5 | Intergration issue with different already existing modules | 3 | 2 | 5
6 | Integration of cross-platform components | 4 | 3 | 7
7 | Lack of technical skills in different programming languages and platforms. | 4 | 3 | 7
8 | Unsurity of team members to continue with the project | 4 | 3 | 7
9 | Unsurity of process areas to be included within the scope of project | 4 | 3 | 7
10 | Ambiguous Requirements | 3 | 2 | 5