## Sprint 2
PUSH NOTIFICATION
SL NO | User Story | Story Point | Task | No of Hours | Planned start Date | Planned End date | Actual Start Date | Actual End Date | Resource
1 | As a User, I want to access the platform on my Android mobile so that I can get updates instantly | 13
|  |  | Create an cross platform mobile application in Microsoft Xamarin(android) . | 16 | 16/12/2016 | 19/12/2016 | 16/12/2016 | 20/12/2016 | Zhao
|  |  | Create a Xamarin project with Android App, | 5 | 20/12/2016 | 20/12/2016 | 20/12/2016 | 21/12/2016 | Zhao
|  |  | Create Mobile Activity to display login page in android | 5 | 20/12/2016 | 21/12/2016 | 21/12/2016 | 21/12/2016 | Zhao
|  |  | Create Mobile Activity to display list of inbox items in android | 5 | 21/12/2016 | 21/12/2016 | 21/12/2016 | 22/12/2016 | Zhao
|  |  | Create Mobile Activity to display details of notifications in android | 8 | 22/12/2016 | 22/12/2016 | 22/12/2016 | 22/12/2016 | Zhao
2 | As a User, I want to access the platform on my iOS mobile so that I can get updates instantly | 13
|  |  | Create an cross platform mobile application in Microsoft Xamarin (ios). | 16 | 16/12/2016 | 19/12/2016 | 16/12/2016 | 19/12/2016 | Vignesh
|  |  | Create a Xamarin project with , iOS App and a Shared Code base | 5 | 20/12/2016 | 20/12/2016 | 20/12/2016 | 20/12/2016 | Vignesh
|  |  | Create Storyboard item to display login page in iOS | 5 | 20/12/2016 | 21/12/2016 | 20/12/2016 | 21/12/2016 | Vignesh
|  |  | Create Storyboard item to display list of inbox items in iOS | 5 | 21/12/2016 | 21/12/2016 | 21/12/2016 | 21/12/2016 | Vignesh
|  |  | Create Storyboard item to display details of notifications in iOS | 8 | 22/12/2016 | 22/12/2016 | 22/12/2016 | 22/12/2016 | Vignesh
3 | As a User, I should be able to login to Instant Edge platform on my android mobile application | 5 | Implement JWT token based authentication in server side. | 1 | 22/12/2016 | 22/12/2016 | 22/12/2016 | 22/12/2016 | Zhao
|  |  | Create a rest end point to authenticate users and generate JWT | 0.5 | 23/12/2016 | 23/12/2016 | 23/12/2016 | 23/12/2016 | Zhao
|  |  | Develop mobile UI to get user credentials | 0.5 | 23/12/2016 | 23/12/2016 | 23/12/2016 | 23/12/2016 | Zhao
|  |  | Communicate with instant edge server and obtain JWT | 1 | 23/12/2016 | 23/12/2016 | 23/12/2016 | 23/12/2016 | Zhao
|  |  | Create rest end point to obtain FCM token from devices | 1 | 23/12/2016 | 23/12/2016 | 23/12/2016 | 23/12/2016 | Zhao
|  |  | Register the FCM token with users list of devices | 5 | 23/12/2016 | 23/12/2016 | 23/12/2016 | 23/12/2016 | Zhao
|  |  | Refresh FCM token in fixed intervals | 3 | 27/12/2016 | 27/12/2016 | 27/12/2016 | 27/12/2016 | Zhao
|  |  | Send a IE generated Device token back to devices | 1 | 27/12/2016 | 27/12/2016 | 27/12/2016 | 27/12/2016 | Zhao
|  |  | From the device send local device token to FCM and obtain FCM token | 1 | 27/12/2016 | 27/12/2016 | 27/12/2016 | 27/12/2016 | Zhao
|  |  | Send the FCM token to server to register for Push Notifications | 0.5 | 27/12/2016 | 27/12/2016 | 27/12/2016 | 27/12/2016 | Zhao
|  |  | Obtain Server generated Device token fro deregistration in the future | 0.5 | 27/12/2016 | 27/12/2016 | 27/12/2016 | 27/12/2016 | Zhao
4 | As a User, I should be able to login to Instant Edge platform on my iOS mobile application | 5 | Implement JWT token based authentication in server side. | 1 | 22/12/2016 | 22/12/2016 | 22/12/2016 | 22/12/2016 | Vignesh
|  |  | Create a rest end point to authenticate users and generate JWT | 0.5 | 23/12/2016 | 23/12/2016 | 23/12/2016 | 23/12/2016 | Vignesh
|  |  | Develop mobile UI to get user credentials | 0.5 | 23/12/2016 | 23/12/2016 | 23/12/2016 | 23/12/2016 | Vignesh
|  |  | Communicate with instant edge server and obtain JWT | 1 | 23/12/2016 | 23/12/2016 | 23/12/2016 | 23/12/2016 | Vignesh
|  |  | Create rest end point to obtain FCM token from devices | 1 | 23/12/2016 | 23/12/2016 | 23/12/2016 | 23/12/2016 | Vignesh
|  |  | Register the FCM token with users list of devices | 5 | 23/12/2016 | 23/12/2016 | 23/12/2016 | 23/12/2016 | Vignesh
|  |  | Refresh FCM token in fixed intervals | 3 | 27/12/2016 | 27/12/2016 | 27/12/2016 | 27/12/2016 | Vignesh
|  |  | Send a IE generated Device token back to devices | 1 | 27/12/2016 | 27/12/2016 | 27/12/2016 | 27/12/2016 | Vignesh
|  |  | From the device send local device token to FCM and obtain FCM token | 1 | 27/12/2016 | 27/12/2016 | 27/12/2016 | 27/12/2016 | Vignesh
|  |  | Send the FCM token to server to register for Push Notifications | 0.5 | 27/12/2016 | 27/12/2016 | 27/12/2016 | 27/12/2016 | Vignesh
|  |  | Obtain Server generated Device token fro deregistration in the future | 0.5 | 27/12/2016 | 27/12/2016 | 27/12/2016 | 27/12/2016 | Vignesh
5 | As a User, I should be able to view my dashboard when I login to the mobile application | 5 | Design the browser wrapper | 3 | 27/12/2016 | 28/12/2016 | 27/12/2016 | 28/12/2016 | Zhao
|  |  | Create a browser wrapper and set URL as IE dashboard page | 5 | 28/12/2016 | 28/12/2016 | 28/12/2016 | 28/12/2016 | Zhao
|  |  | Create a new session in IE using JWT | 2 | 28/12/2016 | 28/12/2016 | 28/12/2016 | 28/12/2016 | Zhao
|  |  | Build and set cookie for the wrapper | 2 | 29/12/2016 | 29/12/2016 | 29/12/2016 | 29/12/2016 | Zhao
|  |  | Load the URL | 1 | 29/12/2016 | 29/12/2016 | 29/12/2016 | 29/12/2016 | Zhao
|  |  | Test the URL | 2 | 29/12/2016 | 29/12/2016 | 29/12/2016 | 29/12/2016 | Zhao
6 | As a User, I want to receive a notification when I receive a new item in my unified box, so that I can handle it on time. | 5 | Create a new FCM message | 5 | 27/12/2016 | 28/12/2016 | 27/12/2016 | 28/12/2016 | Vignesh
|  |  | Send FCM message using serverID, generated during FCM account creation | 5 | 28/12/2016 | 28/12/2016 | 28/12/2016 | 28/12/2016 | Vignesh
|  |  | Test the iOS Feature | 3 | 28/12/2016 | 29/12/2016 | 28/12/2016 | 29/12/2016 | Vignesh
|  |  | Test the Android Feature | 2 | 29/12/2016 | 29/12/2016 | 29/12/2016 | 29/12/2016 | Vignesh
7 | As a User I should be able to logout from the mobile application | 3 | Send IE Generated device token to IE Server's logout endpoint | 3 | 29/12/2016 | 29/12/2016 | 29/12/2016 | 29/12/2016 | Zhao
|  |  | Create rest end point to receive logout requests and deregister device token from the users list of devices | 2 | 30/12/2016 | 30/12/2016 | 30/12/2016 | 30/12/2016 | Zhao
|  |  | Clear all user data from device | 2 | 30/12/2016 | 30/12/2016 | 30/12/2016 | 30/12/2016 | Zhao
|  |  | Test logout functionality | 2 | 30/12/2016 | 30/12/2016 | 30/12/2016 | 30/12/2016 | Zhao
8 | As a User, I want to click on the notification, so that I can be redirected to my unified inbox | 3 | Design the wrapper functionality | 3 | 29/12/2016 | 29/12/2016 | 29/12/2016 | 29/12/2016 | Vignesh
|  |  | Redirect to the wrapper when a notification is clicked | 2 | 30/12/2016 | 30/12/2016 | 30/12/2016 | 30/12/2016 | Vignesh
|  |  | Login automatically using JWT | 2 | 30/12/2016 | 30/12/2016 | 30/12/2016 | 30/12/2016 | Vignesh
|  |  | Test the wrapper functionality | 2 | 30/12/2016 | 30/12/2016 | 30/12/2016 | 30/12/2016 | Vignesh
INCIDENT MANAGEMENT |  | Story Point
9 | As a User, I want redesign the Actor Group Determination table , so as to avoid too much scrolling in the dialogue | 13 | Designing the UI for Actor Group Determination | 7 | 19/12/2016 | 19/12/2016 | 19/12/2016 | 19/12/2016 | vrinda
|  |  | Understanding the variations in the existing system | 6 | 19/12/2016 | 2016-12-20 | 19/12/2016 | 2016-12-20 | vrinda
|  |  | Make user select model and them select procedure | 5 | 2016-12-20 | 2016-12-21 | 2016-12-20 | 2016-12-21 | vrinda
|  |  | Minimising use of scrollers | 5 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | vrinda
|  |  | Making efficient use of Tabs | 6 | 2016-12-21 | 2016-12-22 | 2016-12-21 | 2016-12-22 | vrinda
|  |  | Prototyping page "actorgroupDetermination.xhtml" | 4 | 2016-12-22 | 2016-12-23 | 2016-12-22 | 2016-12-23 | vrinda
|  |  | Prototyping "actorgroupDeterminationList.xhtml" | 6 | 2016-12-23 | 2016-12-23 | 2016-12-23 | 2016-12-23 | vrinda
10 | As an Architect, I want to be able to easily maintain the Actor Group Determination (AGD) without scrolling too much | 13 | Create page for "actorgroupDetermination" | 7 | 19/12/2016 | 19/12/2016 | 19/12/2016 | 19/12/2016 | Rameswari
|  |  | Use tabs instead of scroller | 8 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | Rameswari
|  |  | Create controller "actorActorgroupAssignmentManagedBean" | 4 | 2016-12-20 | 2016-12-21 | 2016-12-20 | 2016-12-21 | Rameswari
|  |  | Change page "actorgroupDetermination.xhtml" | 5 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | Rameswari
|  |  | Create controller actorgroupdeterminationManagedBean" | 8 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | Rameswari
|  |  | Test the Actor Group Determination Table | 4 | 2016-12-23 | 2016-12-23 | 2016-12-23 | 2016-12-23 | Rameswari
|  |  | Regression test the page navigation from other pages | 3 | 2016-12-23 | 2016-12-23 | 2016-12-23 | 2016-12-23 | Rameswari
11 | As a Developer, I should place the edit buttons in such a way that they are consistent throughout the application | 5 | Change the page for "Assign FlowModelFlowProcedureDetermination" | 5 | 2016-12-23 | 2016-12-27 | 2016-12-23 | 2016-12-27 | vrinda
|  |  | Change the page for "FlowModel FlowType assignment" | 4 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | vrinda
|  |  | Change the page for "Create FlowModel" | 3 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | vrinda
|  |  | Test the Functionality | 3 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | vrinda
12 | As a developer, I should change all the flow type to type and flow model to model | 5 | Change the page for "Create Flowtype" | 5 | 2016-12-23 | 2016-12-24 | 2016-12-23 | 2016-12-24 | Rameswari
|  |  | Change the page for "Create FlowModel" | 4 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | Rameswari
|  |  | Change the page for "Assign FlowModelFlowProcedureDetermination" | 3 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | Rameswari
|  |  | Change the page for "FlowModel FlowType assignment" | 3 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | Rameswari
13 | As a developer, I should be sure that the cancel button works consistently for all the pages | 3 | Changes in page for "Maintain Flowfieldgroup" | 3 | 2016-12-28 | 2016-12-29 | 2016-12-28 | 2016-12-29 | vrinda
|  |  | Changes in page for "Maintain Actorgroup" | 2 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | vrinda
|  |  | Testing the button in all the pages | 4 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | vrinda
14 | As a developer, I want to be sure that the delete button in Assignment of Flow Step to Flow Procedure should delete the Step. | 3 | Assignment of Flow Step to Flow Procedure | 3 | 2016-12-28 | 2016-12-29 | 2016-12-28 | 2016-12-29 | Rameswari
|  |  | View the selected procedure | 2 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | Rameswari
|  |  | link the step to procedure | 2 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | Rameswari
|  |  | Delete the step within the procedure | 1 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | Rameswari
|  |  | Testing the button in all the pages | 1 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | Rameswari
15 | As a developer, I should differentiate Message overview, Attachment and message History , so as not to confuse the user | 5 | Changes in Create Incident | 4 | 2016-12-29 | 30/12/2016 | 2016-12-29 | 30/12/2016 | vrinda
|  |  | Changes in "Create Incident Managed bean" | 4 | 30/12/2016 | 30/12/2016 | 30/12/2016 | 30/12/2016 | vrinda
|  |  | Changes in "Create Flow Procedure Managed Bean" | 3 | 30/12/2016 | 2016-12-31 | 30/12/2016 | 2016-12-31 | vrinda
|  |  | Changes in "Flow procedure exception" | 2 | 2016-12-31 | 2016-12-31 | 2016-12-31 | 2016-12-31 | vrinda
|  |  | Changes in "Flow procedure service" | 1 | 2016-12-31 | 2016-12-31 | 2016-12-31 | 2016-12-31 | vrinda
|  |  | Testing the functionality | 1 | 2016-12-31 | 2016-12-31 | 2016-12-31 | 2016-12-31 | vrinda
16 | As a developer, I should have some for Assignment of Flow Model to Flow Type the flow model list | 5 | Assignment of "FlowModel FlowType" | 4 | 2016-12-29 | 30/12/2016 | 2016-12-29 | 30/12/2016 | Rameswari
|  |  | Assign flow procedure to model page. | 4 | 30/12/2016 | 30/12/2016 | 30/12/2016 | 30/12/2016 | Rameswari
|  |  | Changes in page for "Create Flowfieldgroup" | 4 | 30/12/2016 | 2016-12-31 | 30/12/2016 | 2016-12-31 | Rameswari
|  |  | Testing the button in all the pages | 3 | 2016-12-31 | 2016-12-31 | 2016-12-31 | 2016-12-31 | Rameswari
Date | Rameswari | Vignesh | Zhao | Vrinda | Total Burndown
16/12/2016 | 8 | 8 | 7 | 9 | 32
19/12/2016 | 10 | 8 | 8 | 11 | 37
20/12/2016 | 11 | 8 | 8 | 8 | 35
21/12/2016 | 8 | 8 | 6 | 8 | 30
22/12/2016 | 10 | 11 | 11 | 9 | 41
23/12/2016 | 8 | 2 | 5 | 8 | 23
27/12/2016 | 7 | 5 | 3 | 8 | 23
28/12/2016 | 11 | 10 | 12 | 9 | 42
29/12/2016 | 11 | 11 | 12 | 5 | 39
30/12/2016 | 11 | 12 | 12 | 8 | 43

## Sprint 3
Sl No | User Story | Story Point | Task | No of Hours | Planned start Date | Planned End date | Actual start Date | Actual End date | Resource
1 | As a user I should be able to configure FlowType of an incident | 13 | Create page for "Create Flowtype" | 2 | 2017-09-01 | 2017-09-01 | 16/01/2017 | 16/01/2017 | Rameswari
|  |  | Create page for "Edit Flowtype" | 3 | 2017-09-01 | 2017-09-01 | 16/01/2018 | 16/01/2018 | Rameswari
|  |  | Create page for "Display Flowtype" | 1 | 2017-09-01 | 2017-09-01 | 16/01/2019 | 16/01/2019 | Rameswari
|  |  | Create page for "Copy Flowtype" | 1 | 2017-09-01 | 2017-09-01 | 17/01/2017 | 17/01/2017 | Rameswari
|  |  | Create page for "Maintain Flowtype" | 1 | 2017-09-01 | 2017-09-01 | 17/01/2017 | 17/01/2017 | Rameswari
|  |  | Create page for "FlowtypeList " | 1 | 2017-10-01 | 2017-10-01 | 17/01/2017 | 17/01/2017 | Rameswari
|  |  | Create controller "FlowtypeManagedBean" | 8 | 2017-10-01 | 2017-11-01 | 17/01/2017 | 17/01/2017 | Rameswari
|  |  | Create exceptions for "Flowtype" | 1 | 2017-11-01 | 2017-11-01 | 18/01/2017 | 18/01/2017 | Rameswari
|  |  | Create service interface "FlowtypeService" | 8 | 2017-11-01 | 2017-12-01 | 18/01/2017 | 18/01/2017 | Rameswari
|  |  | Create service "DefaultFlowtypeService" | 8 | 2017-12-01 | 13/01/2017 | 19/01/2017 | 19/01/2017 | Rameswari
|  |  | Create domain entity Flowtype" | 1 | 13/01/2017 | 13/01/2017 | 20/01/2017 | 20/01/2017 | Rameswari
|  |  | Test Flowtype | 4 | 13/01/2017 | 13/01/2017 | 20/01/2017 | 20/01/2017 | Rameswari
2 | As a user I chould be able to configure FlowModel of an incident | 8 | Create page for "Create FlowModel" | 1 | 13/01/2017 | 13/01/2017 | 20/01/2017 | 20/01/2017 | Rameswari
|  |  | Create page for "Edit Flowmodel" | 1 | 16/01/2017 | 16/01/2017 | 20/01/2017 | 20/01/2017 | Rameswari
|  |  | Create page for "Display Flowmodel" | 1 | 16/01/2017 | 16/01/2017 | 20/01/2017 | 20/01/2017 | Rameswari
|  |  | Create page for "Copy Flowmodel" | 1 | 16/01/2017 | 16/01/2017 | 20/01/2017 | 20/01/2017 | Rameswari
|  |  | Create page for "Maintain FlowModel" | 1 | 16/01/2017 | 16/01/2017 | 20/01/2017 | 20/01/2017 | Rameswari
|  |  | Create page for "FlowmodelList " | 1 | 16/01/2017 | 16/01/2017 | 20/01/2017 | 20/01/2017 | Rameswari
|  |  | Create controller "FlowmodelManagedBean" | 4 | 16/01/2017 | 17/01/2017 | 23/01/2017 | 23/01/2017 | Rameswari
|  |  | Create exceptions for "Flowmodel" | 1 | 17/01/2017 | 17/01/2017 | 23/01/2017 | 23/01/2017 | Rameswari
|  |  | Create service interface "FlowmodelService" | 4 | 17/01/2017 | 17/01/2017 | 24/01/2017 | 24/01/2017 | Rameswari
|  |  | Create service "DefaultFlowmodelService" | 4 | 17/01/2017 | 18/01/2017 | 24/01/2017 | 24/01/2017 | Rameswari
|  |  | Create domain entity Flowmodel" | 1 | 18/01/2017 | 18/01/2017 | 25/01/2017 | 25/01/2017 | Rameswari
|  |  | Test Flowmodel | 4 | 18/01/2017 | 18/01/2017 | 25/01/2017 | 25/01/2017 | Rameswari
3 | As a user I should be able to assign Flow model to Flow Type | 5 | Create page for "FlowModel FlowType assignment" | 1 | 18/01/2017 | 18/01/2017 | 25/01/2017 | 25/01/2017 | Rameswari
|  |  | Create controller "FlowmodelFlowTypeManagedBean" | 4 | 19/01/2017 | 19/01/2017 | 25/01/2017 | 25/01/2017 | Rameswari
|  |  | Create exceptions for "FlowmodelFlowtype" | 1 | 19/01/2017 | 19/01/2017 | 26/01/2017 | 26/01/2017 | Rameswari
|  |  | Create service interface "FlowmodelFlowtypeService" | 3 | 19/01/2017 | 19/01/2017 | 26/01/2017 | 26/01/2017 | Rameswari
|  |  | Create service "DefaultFlowmodelFlowtypeService" | 3 | 20/01/2017 | 20/01/2017 | 26/01/2017 | 26/01/2017 | Rameswari
|  |  | Create domain entity FlowmodelFlowtype" | 1 | 20/01/2017 | 20/01/2017 | 27/01/2017 | 27/01/2017 | Rameswari
|  |  | Test Flowmodel to flow type assignment | 2 | 20/01/2017 | 20/01/2017 | 27/01/2017 | 27/01/2017 | Rameswari
Rameswari
4 | As a user I should be able to define and assign procedure to Flow model | 13 | Create page for "Assign FlowModelFlowProcedureDetermination" | 4 | 2017-09-01 | 2017-09-01 | 16/01/2017 | 16/01/2017 | Vrinda
|  |  | Create controller "FlowprocedureManagedBean" | 8 | 2017-09-01 | 2017-10-01 | 16/01/2017 | 17/01/2017 | Vrinda
|  |  | Create exceptions for "Flow Procedure" | 3 | 2017-10-01 | 2017-10-01 | 17/01/2017 | 17/01/2017 | Vrinda
|  |  | Create service interface "FlowprocedureService" | 8 | 2017-10-01 | 2017-11-01 | 17/01/2017 | 18/1/2017 | Vrinda
|  |  | Create service "DefaultFlowprocedureService" | 8 | 2017-11-01 | 2017-12-01 | 18/1/2017 | 19/01/2017 | Vrinda
|  |  | Create domain entity Flowprocedure" | 4 | 2017-12-01 | 13/01/2017 | 19/01/2017 | 20/01/2017 | Vrinda
|  |  | Test Flowprocedue to flow model assignment | 4 | 13/01/2017 | 13/01/2017 | 20/01/2017 | 20/01/2017 | Vrinda
Vrinda
5 | As a user I should be able to define and assign step to Flow procedure | 8 | Create page for "Assign FlowProcedureFlowstepDetermination" | 2 | 13/01/2017 | 16/01/2017 | 20/01/2017 | 23/01/2017 | Vrinda
|  |  | Create controller "FlowstepManagedBean" | 4 | 16/01/2017 | 16/01/2017 | 23/01/2017 | 23/01/2017 | Vrinda
|  |  | Create exceptions for "Flow step" | 2 | 16/01/2017 | 16/01/2017 | 23/01/2017 | 23/01/2017 | Vrinda
|  |  | Create service interface "FlowstepService" | 5 | 16/01/2017 | 17/01/2017 | 23/01/2017 | 24/01/2017 | Vrinda
|  |  | Create service "DefaultFlowstepService" | 5 | 17/01/2017 | 17/01/2017 | 24/01/2017 | 24/01/2017 | Vrinda
|  |  | Create domain entity Flowstep" | 2 | 17/01/2017 | 17/01/2017 | 24/01/2017 | 24/01/2017 | Vrinda
|  |  | Test FlowStep to flow procedure assignment | 4 | 18/01/2017 | 18/01/2017 | 25/01/2017 | 25/01/2017 | Vrinda
Vrinda
6 | As a user I should be able to design the flow field group | 5 | Create page for "Create Flowfieldgroup" | 1 | 18/01/2017 | 18/01/2017 | 25/01/2017 | 25/01/2017 | Vrinda
|  |  | Create page for "Edit Flowfieldgroup" | 0.5 | 18/01/2017 | 18/01/2017 | 25/01/2017 | 25/01/2017 | Vrinda
|  |  | Create page for "Display Flowfieldgroup" | 0.5 | 18/01/2017 | 18/01/2017 | 25/01/2017 | 25/01/2017 | Vrinda
|  |  | Create page for "Copy Flowfieldgroup" | 1 | 18/01/2017 | 18/01/2017 | 25/01/2017 | 25/01/2017 | Vrinda
|  |  | Create page for "Maintain Flowfieldgroup" | 1 | 18/01/2017 | 18/01/2017 | 25/01/2017 | 25/01/2017 | Vrinda
|  |  | Create page for "FlowfieldgroupList " | 3 | 19/01/2017 | 19/01/2017 | 26/01/2017 | 26/01/2017 | Vrinda
|  |  | Create controller "FlowfieldgroupManagedBean" | 3 | 19/01/2017 | 19/01/2017 | 26/01/2017 | 26/01/2017 | Vrinda
|  |  | Create exceptions for "Flowfieldgroup" | 1 | 19/01/2017 | 19/01/2017 | 26/01/2017 | 26/01/2017 | Vrinda
|  |  | Create service interface "FlowfieldgroupService" | 1 | 19/01/2017 | 19/01/2017 | 26/01/2017 | 26/01/2017 | Vrinda
|  |  | Create service "DefaultFlowfieldgroupService" | 2 | 20/01/2017 | 20/01/2017 | 27/01/2018 | 27/01/2018 | Vrinda
|  |  | Create domain entity Flowfieldgroup" | 2 | 27/01/2018 | 27/01/2018 | 27/01/2018 | 27/01/2018 | Vrinda
|  |  | Test Flowfieldgroup | 2 | 27/01/2019 | 27/01/2019 | 27/01/2019 | 27/01/2019 | Vrinda
7 | As a user I should be able to design the flow field control screen layout | 8 | Create page for "create FlowfieldcontrolDetermination" | 2 | 2017-09-01 | 2017-09-01 | 16/01/2017 | 16/01/2017 | zhao
|  |  | Create controller "FlowfieldcontrolManagedBean" | 4 | 2017-09-01 | 2017-09-01 | 16/01/2017 | 17/01/2017 | zhao
|  |  | Create exceptions for "Flowfieldcontrol" | 2 | 2017-10-01 | 2017-10-01 | 17/01/2017 | 17/01/2017 | zhao
|  |  | Create service interface "FlowfieldcontrolService" | 5 | 2017-10-01 | 2017-10-01 | 17/01/2017 | 18/1/2017 | zhao
|  |  | Create service "DefaultFlowfieldcontrolService" | 5 | 2017-10-01 | 2017-11-01 | 18/1/2017 | 19/01/2017 | zhao
|  |  | Create domain entity Flowfieldcontrol" | 2 | 2017-11-01 | 2017-11-01 | 19/01/2017 | 20/01/2017 | zhao
|  |  | Test screen layout for flow field control | 4 | 2017-11-01 | 2017-11-01 | 20/01/2017 | 20/01/2017 | zhao
8 | As a user I should be able to configure flow approver. | 13 | Create page for "actorgroupDetermination" | 2 | 2017-11-01 | 2017-12-01 | 20/01/2017 | 23/01/2017 | zhao
|  |  | Create controller actorgroupdeterminationManagedBean" | 3 | 2017-12-01 | 2017-12-01 | 23/01/2017 | 23/01/2017 | zhao
|  |  | Create exceptions for "actorgroupdetermination" | 1 | 2017-12-01 | 2017-12-01 | 23/01/2017 | 23/01/2017 | zhao
|  |  | Create service interface "actorgroupdeterminationService" | 1 | 2017-12-01 | 2017-12-01 | 23/01/2017 | 23/01/2017 | zhao
|  |  | Create service "DefaultactorgroupdeterminationService" | 1 | 2017-12-01 | 2017-12-01 | 23/01/2017 | 23/01/2017 | zhao
|  |  | Create domain entity actorgroupdetermination" | 1 | 2017-12-01 | 2017-12-01 | 23/01/2017 | 23/01/2017 | zhao
|  |  | Create page for "actorgroupDeterminationList" | 8 | 13/01/2017 | 13/01/2017 | 24/01/2017 | 24/01/2017 | zhao
|  |  | Create controller actorgroupdeterminationListManagedBean" | 1 | 16/01/2017 | 16/01/2017 | 24/01/2017 | 24/01/2017 | zhao
|  |  | Create exceptions for "actorgroupdeterminationList" | 8 | 16/01/2017 | 17/01/2017 | 24/01/2017 | 24/01/2017 | zhao
|  |  | Create service interface "actorgroupdeterminationListService" | 8 | 17/01/2017 | 18/01/2017 | 25/01/2017 | 25/01/2017 | zhao
|  |  | Create service "DefaultactorgroupdeterminationListService" | 1 | 18/01/2017 | 18/01/2017 | 25/01/2017 | 25/01/2017 | zhao
|  |  | Create domain entity actorgroupdeterminationList" | 4 | 18/01/2017 | 18/01/2017 | 26/01/2017 | 26/01/2017 | zhao
|  |  | Test message determination logic | [5 empty] | zhao
9 | As a user I should be able to create a incident request | 5 | Select a flow type from a flow type list | 5 | 18/01/2017 | 19/01/2017 | 26/01/2017 | 26/01/2017 | zhao
|  |  | Select a flow model from flow model list | 3 | 19/01/2017 | 19/01/2017 | 26/01/2017 | 26/01/2017 | zhao
|  |  | View the list of procedure for the selected model | 2 | 19/01/2017 | 19/01/2017 | 27/01/2017 | 27/01/2017 | zhao
|  |  | enter details of the incident | 3 | 20/01/2017 | 20/01/2017 | 27/01/2017 | 27/01/2017 | zhao
|  |  | Incident should be created | 2 | 20/01/2017 | 20/01/2017 | 27/01/2017 | 27/01/2017 | zhao
zhao
10 | AS a service desk manager I should be able to create actor groups | 13 | Create page for "Create Actorgroup" | 2 | 2017-09-01 | 2017-09-01 | 16/1/2017 | 16/1/2017 | Vignesh
|  |  | Create page for "Edit Actorgroup" | 3 | 2017-09-01 | 2017-09-01 | 16/1/2017 | 16/1/2017 | Vignesh
|  |  | Create page for "Display Actorgroup" | 1 | 2017-09-01 | 2017-09-01 | 16/1/2017 | 16/1/2017 | Vignesh
|  |  | Create page for "Copy Actorgroup" | 1 | 2017-09-01 | 2017-09-01 | 16/1/2017 | 16/1/2017 | Vignesh
|  |  | Create page for "Maintain Actorgroup" | 1 | 2017-09-01 | 2017-09-01 | 16/1/2017 | 16/1/2017 | Vignesh
|  |  | Create page for "ActorgroupList " | 1 | 2017-10-01 | 2017-10-01 | 17/1/2017 | 17/1/2017 | Vignesh
|  |  | Create controller "ActorgroupManagedBean" | 8 | 2017-10-01 | 2017-11-01 | 17/1/2017 | 18/1/2017 | Vignesh
|  |  | Create exceptions for "Actorgroup" | 1 | 2017-11-01 | 2017-11-01 | 18/1/2017 | 18/1/2017 | Vignesh
|  |  | Create service interface "ActorgroupService" | 8 | 2017-12-01 | 2017-12-01 | 19/1/2017 | 19/1/2017 | Vignesh
|  |  | Create service "DefaultActorgroupService" | 8 | 13/01/2017 | 13/01/2017 | 20/01/2017 | 20/01/2017 | Vignesh
|  |  | Create domain entityActorgroup" | 1 | 16/01/2017 | 16/01/2017 | 23/01/2017 | 23/01/2017 | Vignesh
|  |  | Test Actorgroup | 4 | 16/01/2017 | 16/01/2017 | 23/01/2017 | 23/01/2017 | Vignesh
11 | AS a service desk manager I should be able to assign actors to a actor group | 8 | Create page for "Assign actorActorgroupAssignment" | 2 | 16/01/2017 | 16/01/2017 | 23/01/2017 | 23/01/2017 | Vignesh
|  |  | Create controller "actorActorgroupAssignmentManagedBean" | 4 | 16/01/2017 | 17/01/2017 | 23/01/2017 | 24/01/2017 | Vignesh
|  |  | Create exceptions for "actorActorgroupAssignment" | 2 | 17/01/2017 | 17/01/2017 | 24/01/2017 | 24/01/2017 | Vignesh
|  |  | Create service interface "actorActorgroupAssignmentService" | 5 | 17/01/2017 | 18/01/2017 | 24/01/2017 | 25/01/2017 | Vignesh
|  |  | Create service "DefaultactorActorgroupAssignmentService" | 5 | 18/01/2017 | 18/01/2017 | 25/01/2017 | 25/01/2017 | Vignesh
|  |  | Create domain entity actorActorgroupAssignment" | 2 | 19/01/2017 | 19/01/2017 | 26/01/2017 | 26/01/2017 | Vignesh
|  |  | Test actor to actor group assignment | 4 | 19/01/2017 | 19/01/2017 | 26/01/2017 | 26/01/2017 | Vignesh
Vignesh
12 | AS a service desk manager I should be able to assign users to actors | 5 | Create page for "Create Actor" | 1 | 19/01/2017 | 19/01/2017 | 26/01/2017 | 26/01/2017 | Vignesh
|  |  | Create page for "Edit Actor" | 0.5 | 19/01/2017 | 19/01/2017 | 26/01/2017 | 26/01/2017 | Vignesh
|  |  | Create page for "Display Actor" | 0.5 | 19/01/2017 | 19/01/2017 | 26/01/2017 | 26/01/2017 | Vignesh
|  |  | Create page for "Copy Actor" | 1 | 20/01/2017 | 20/01/2017 | 27/01/2017 | 27/01/2017 | Vignesh
|  |  | Create page for "Maintain Actorgroup" | 1 | 20/01/2017 | 20/01/2017 | 27/01/2017 | 27/01/2017 | Vignesh
|  |  | Create page for "ActorList " | 1 | 20/01/2017 | 20/01/2017 | 27/01/2017 | 27/01/2017 | Vignesh
|  |  | Create controller "ActorgroupManagedBean" | 1 | 20/01/2017 | 20/01/2017 | 27/01/2017 | 27/01/2017 | Vignesh
|  |  | Create exceptions for "Actor" | 1 | 20/01/2017 | 20/01/2017 | 27/01/2017 | 27/01/2017 | Vignesh
|  |  | Create service interface "ActorService" | 1 | 20/01/2017 | 20/01/2017 | 27/01/2017 | 27/01/2017 | Vignesh
|  |  | Create service "DefaultActorgroupService" | 0.5 | 20/01/2017 | 20/01/2017 | 27/01/2017 | 27/01/2017 | Vignesh
|  |  | Create domain entityActor" | 0.5 | 20/01/2017 | 20/01/2017 | 27/01/2017 | 27/01/2017 | Vignesh
|  |  | Test Actor | 2 | 20/01/2017 | 20/01/2017 | 27/01/2017 | 27/01/2017 | Vignesh
Date | Rameswari | Vignesh | Zhao | Vrinda | Total Burndown
16/01/2017 | 8 | 8 | 8 | 8 | 32
17/01/2017 | 11 | 8 | 7 | 7 | 33
18/01/2017 | 10 | 7 | 8 | 9 | 34
19/01/2017 | 8 | 9 | 8 | 8 | 33
20/01/2017 | 11 | 8 | 8 | 8 | 35
21/01/2017
22/01/2017
23/01/2017 | 5 | 11 | 11 | 7 | 34
24/01/2017 | 8 | 9 | 9 | 7 | 33
25/01/2017 | 10 | 8 | 8 | 11 | 37
26/01/2017 | 7 | 8 | 12 | 8 | 35
27/01/2017 | 8 | 6 | 7 | 9 | 30

## Sprint Burndown 2-3
SPRINT 2 BURNDOWN
| Days | Planned Hours Burndown | Actual Hours burndown | Dates
| 0 | 320 | 345 | 16/12/2016
| 1 | 288 | 313 | 19/12/2016
| 2 | 256 | 276 | 20/12/2016
| 3 | 224 | 241 | 21/12/2016
| 4 | 192 | 211 | 22/12/2016
| 5 | 160 | 170 | 23/12/2016
| 6 | 128 | 146 | 27/12/2016
| 7 | 96 | 123 | 28/12/2016
| 8 | 64 | 81 | 29/12/2016
| 9 | 32 | 42 | 30/12/2016
| 10 | 0 | 0
SPRINT 3 BURNDOWN
| Days | Planned Hours Burndown | Actual Hours burndown | Dates
| 0 | 320 | 336 | 2017-09-01
| 1 | 288 | 336 | 2017-10-01
| 2 | 256 | 336 | 2017-11-01
| 3 | 224 | 336 | 2017-12-01
| 4 | 192 | 336 | 13/1/2017
| 5 | 160 | 336 | 16/1/2017
| 6 | 128 | 304 | 17/1/2017
| 7 | 96 | 271 | 18/1/2017
| 8 | 64 | 237 | 19/1/2017
| 9 | 32 | 204 | 20/1/2017
| 10 | 0 | 169 | 23/1/2017
| 11 | 0 | 135 | 24/1/2017
| 12 | 0 | 102 | 25/1/2017
| 13 | 0 | 65 | 26/1/2017
| 14 | 0 | 30 | 27/1/2017
| 15 | 0 | 0 | 28/1/2017

## Sprint 4
Status | JIRA ID | Group | User Story | Task | Effort Estimate(days) | Planned start Date | Planned End date | Actual start Date | Actual End date | Resource
MUST | IE-1517 | User Action | As a architect , i want to be able to configure User action | 1.Identify and design User action Type: Custom, OnHold ,Close, SaveAsDraft (Type)+parameters () + caching strategy | 1 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | Vignesh
|  |  | I want to specify User Action Consequence (from root data) for User Actions(Configuration) | 2. Domain Model Changes: Add UserAction, UserActionType, UserActionTypeParameters | 1 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | Vrinda
|  |  | I should be prompted the appropriate Procedure and step (in case of multiple destinations) where the incident has to be routed(dropdown) | 3. Interfaces - Create interfaces for UA Services (UserActionService, UATypeService, UATypeParameterService) | 1 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | Vignesh
|  |  | I want to specify destination(proc->step combination) for user-actions | 4. Services - Implement all iterfaces for UserAction (DefaultUAService, DefaultUATypeService, DefaultUATypeParameterService | 1 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | Vrinda
|  |  | I want to maintain(CRUD) UserActions (name, "consequence" [hard-coded consequences]) | 5. Controllers - Create controllers to manage strategies/behavior of UA (logic + navigation) - update flow status(cascade) - create flow items - dispatch flow items | 1 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | Vignesh
|  |  | I want to maintain(CRUD) UserActions (name, "consequence" [getting away from hard-coded consequences]) | 6. UT - Write tests to verify EJB transaactions and controller methods | 1 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | Vrinda
|  |  |  | 7. Converters - Write required converters for managed beans (TBD) | 1 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | Vignesh
|  |  |  | 8. Validators - Implement validators for UI fields and other input data | 1 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | Vrinda
|  |  |  | 9. Utilities - Write required utilities for UserAction retrieval (TBD) | 1 | 2017-02-17 | 2017-02-17 | 2017-02-16 | 2017-02-16 | Vignesh
|  |  |  | 10. Applicable patterns - Identify design patterns applicable and implement | 1 | 2017-02-17 | 2017-02-17 | 2017-02-16 | 2017-02-16 | Vrinda
|  |  |  | 11. Web Pages - Create xhtml pages for root users, architect and end user to interact with the platform | 1 | 2017-02-20 | 2017-02-20 | 2017-02-17 | 2017-02-17 | Vignesh
|  |  |  | 12. Pages design - Decide and implement pages design | 1 | 2017-02-20 | 2017-02-20 | 2017-02-17 | 2017-02-17 | Vrinda
|  |  |  | 13. Data standards - Prepare and load best practise data for demonstration + document required data(root) | 1 | 2017-02-21 | 2017-02-21 | 2017-02-20 | 2017-02-20 | Vignesh
|  |  |  | 14. User acceptance criteria - Define acceptance criteria and conduct test to record scores | 1 | 2017-02-21 | 2017-02-21 | 2017-02-20 | 2017-02-20 | Vrinda
|  |  |  | 15. Test cases - Run all tests and make changes to optimize the solution | 1 | 2017-02-22 | 2017-02-22 | 2017-02-21 | 2017-02-21 | Vignesh
|  |  |  | 16. Security - Run security tests to confirm the integrity of the solution | 1 | 2017-02-22 | 2017-02-22 | 2017-02-21 | 2017-02-21 | Vrinda
|  |  |  | 17. Documentation - Document the design and analysis as well as User guide if applicable | 1 | 2017-02-23 | 2017-02-23 | 2017-02-22 | 2017-02-22 | Vrinda
MUST | IE-1335 | Routing Logic | I should be able to define the entry point for workflow (taken as the first proc->step) | 1.Identify and design Routing logic : skeleton(scaffold), UI design decisions | 1 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | Zhao
|  |  | I should be able to define the termination point for workflow (taken as the last proc->step) | 2.Domain model changes design | 1 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | Rameswari
|  |  | I should be able to provide incident details(title, description, category, attachment, asset type, priority, geographical location) | 3. Applicable patterns - Identify design patterns applicable and implement | 1 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | Zhao
|  |  | I should be able to view the status of a particular incident | 4. Create Service Interfaces for persistFlowItem , persistFlow , SaveAsDraft | 1 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | Rameswari
|  |  | I should be able to assign/set/update classification data to the incident(trigger a re-determination of message) | 5.Controller logic : Segregate common function and implementation | 1 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | Zhao
|  |  | I want to be able to route messages to a destination based on my action | 6.Controller logic : dispatch , forward | 1 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | Rameswari
|  |  | I should not be allowed to perform User Action which has no User to act on (UI Alert) | 7. Controller logic : Unresolvable,accept, saveasdraft, reject | 1 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | Zhao
|  |  |  | 8.Controller logic : on-hold , close, resolve | 1 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | Rameswari
|  |  |  | 9.Controller logic : escalate | 1 | 2017-02-17 | 2017-02-17 | 2017-02-16 | 2017-02-16 | Zhao
|  |  |  | 10. Interfaces - Create interfaces for Services to implement routing logic | 1 | 2017-02-17 | 2017-02-17 | 2017-02-17 | 2017-02-17 | Rameswari
|  |  |  | 11. Services - Implement the services,DAO for Controller logic - part 1 | 1 | 2017-02-20 | 2017-02-20 | 2017-02-17 | 2017-02-17 | Zhao
|  |  |  | 12. Services - Implement the services,DAO for Controller logic - part 2 | 1 | 2017-02-20 | 2017-02-20 | 2017-02-17 | 2017-02-17 | Rameswari
|  |  |  | 13. UT - Write tests to verify EJB transaactions | 1 | 2017-02-21 | 2017-02-21 | 2017-02-20 | 2017-02-20 | Zhao
|  |  |  | 14. UT - Write tests to verify Controller logic | 1 | 2017-02-21 | 2017-02-21 | 2017-02-20 | 2017-02-20 | Rameswari
|  |  |  | 15. Converters - Write required converters for managed beans (TBD) | 1 | 2017-02-22 | 2017-02-22 | 2017-02-21 | 2017-02-21 | Zhao
|  |  |  | 16. Validators - Implement validators for UI fields and other input data | 1 | 2017-02-22 | 2017-02-22 | 2017-02-21 | 2017-02-21 | Rameswari
|  |  |  | 17. Utilities - Write required utilities for UserAction retrieval (TBD) | 1 | 2017-02-23 | 2017-02-23 | 2017-02-22 | 2017-02-22 | Zhao
|  |  |  | 18. Web Pages : Create Xhtml pages : CreateWorkflowIncident.xhtml | 1 | 2017-02-23 | 2017-02-23 | 2017-02-22 | 2017-02-22 | Rameswari
|  |  |  | 19. Web Pages : Create Xhtml pages : UIComposition-page-procedure.xhtml | 1 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | Zhao
|  |  |  | 20. Web Pages : Create Xhtml pages :UIComposition-page-Message-History.xhtml | 0.5 | 2017-02-24 | 2017-02-24 | 2017-02-23 | 2017-02-23 | Rameswari
|  |  |  | 21. Web Pages : Create Xhtml pages : UIComposition-message-tree.xhtml | 0.5 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | Zhao
|  |  |  | 22. Web Pages : Create Xhtml pages : UIComposition -AttachmentsOverview.xhtml | 0.5 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | Rameswari
|  |  |  | 23.Data standards - Prepare and load best practise data for demonstration | 0.5 | 2017-02-24 | 2017-02-24 | 2017-02-22 | 2017-02-22 | Vignesh
|  |  |  | 24. User acceptance criteria - Define acceptance criteria and conduct test to record scores | 0.5 | 2017-02-24 | 2017-02-24 | 2017-02-23 | 2017-02-23 | Vignesh
|  |  |  | 25. Test cases - Run all tests and make changes to optimize the solution | 0.5 | 2017-02-24 | 2017-02-24 | 2017-02-23 | 2017-02-23 | Vrinda
|  |  |  | 26.Security - Run security tests to confirm the integrity of the solution | 0.5 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | Vignesh
|  |  |  | 27. Documentation - Document the design and analysis as well as User guide if applicable | 0.5 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | Vrinda
40
320
Total No of Working day in Sprint 4 = 15 Days
No if of Hours per day = 8 Hr
No of Resource = 4
Total No of Man Hour for sprint 1= 10*8*4 = 480
Effort per person for Sprint Planning and retrospective =2 day =
Total effort for Sprint Planning and Retrospective = 8*4 * 2= 64 Hr
Requirement gathering, User stories analysis and design = 3 day = 3*4*8 = 96
Total hour Remaining = 480 – (64+96) = 320 Hr
Sprint Capacity = 320 Hr.
Date | Rameswari | Vignesh | Zhao | Vrinda | Total Burndown
2017-02-13 | 9 | 9 | 9 | 8 | 35 | 348
2017-02-14 | 9 | 9 | 9 | 10 | 37 | 310
2017-02-15 | 7 | 7 | 7 | 7 | 28 | 274
2017-02-16 | 7 | 8 | 8 | 7 | 30 | 235
2017-02-17 | 10 | 9 | 9 | 10 | 38 | 200
2017-02-20 | 8 | 8 | 8 | 8 | 32 | 168
2017-02-21 | 9 | 9 | 9 | 8 | 35 | 130
2017-02-22 | 10 | 10 | 10 | 9 | 39 | 100
2017-02-23 | 9 | 9 | 9 | 9 | 36 | 72
2017-02-24 | 10 | 9 | 9 | 10 | 38 | 35
348

## Sprint 5
Status | JIRA ID | Group | User Story | Task | Effort Estimate(days) | Total Estimate | Planned start Date | Planned End date | Actual start Date | Actual End date | Resource
MUST | IE-1433 | TIMELINE, TREE, HISTORY, ATTACHMENT | I must be able to visualize the incident as History+Forward Path (Tree, History->Timeline) | Create tab for viewing tree(only until step) and timeline for the flow in flow page | 0.5 | 6.5 | 2017-03-15 | 2017-03-15 | 2017-03-15 | 2017-03-15 | Zhao
|  |  |  | Implement method to identify happy path in the configuration | 1 |  | 2017-03-15 | 2017-03-16 | 2017-03-15 | 2017-03-16 | Zhao
|  |  |  | Replace history with the timeline (get and render all flow items) | 1 |  | 2017-03-16 | 2017-03-17 | 2017-03-16 | 2017-03-17 | Zhao
|  |  |  | Identify UI components to use with the Tree and Timeline | 0.5 |  | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | Zhao
|  |  |  | Write Backing Bean for the UI | 1 |  | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Rameswari
|  |  |  | Write unit test cases for Tree and Timeline | 0.5 |  | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | Rameswari
|  |  |  | Identify integration points for Attachment of files | 1 |  | 2017-03-02 | 2017-03-03 | 2017-03-02 | 2017-03-03 | Rameswari
|  |  |  | Perform testing for all tasks above | 1 |  | 2017-03-03 | 2017-03-06 | 2017-03-03 | 2017-03-06 | Rameswari
MUST | IE-1439 | Individual Inbox | I should only be able to view the list of incidents I'm authorized to | Identify all the criteria for incident filtering | 0.5 | 2.5 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | Rameswari
|  |  | I should be able to filter the list of incidents based on dynamic criteria | Write JPQL/UI changes in Unified inbox to filter inbox items using the criteria listed above | 0.5 |  | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | Rameswari
|  |  |  | Write unit test to test all the criteria | 0.5 |  | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | Rameswari
|  |  |  | Perform testing for all tasks above | 1 |  | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | Rameswari
MUST | IE-1527 | AG Inbox, Dispatch strategy (Single Actor Flag, Auto/Manual assignment of actors),Dispatch cockpit for manual overrides(Service manager), | I should be able to filter the list of incidents based on dynamic criteria | Create separate inbox for actor group (UI) | 1 | 22 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Vignesh
|  |  | I want to specify single actor group flag as a strategy for AGD (acknowledge by one is enough or everyone has to acknowledge) | Create dispatch page for manager (UI) | 1 |  | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | Vignesh
|  |  | I want to specify whether the messages have to be dispatched automatically or manually | Create managed beans to back the views | 2 |  | 2017-03-03 | 2017-03-06 | 2017-03-03 | 2017-03-06 | Vignesh
|  |  | I want to see all the flows from my associated actor groups (AG Inbox) | Identify and implement domain model changes | 2 |  | 2017-03-07 | 2017-03-08 | 2017-03-07 | 2017-03-08 | Vignesh
|  |  | I should assign manually, an incident to an actor of the determined actor group (override/dispatch) (an editable queue/list) | write EJB, Exception classes to accommodate new requirements | 1 |  | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | Vignesh
|  |  | I should be able to classify an incident as a "VIP" incident | Refactor the message det page and the managed bean to include the single actor flag | 2 |  | 2017-03-10 | 2017-03-13 | 2017-03-10 | 2017-03-13 | Vignesh
|  |  | I should have a cockpit to view all incidents (potential reuse of UI components) | Refactor the routing logic to accommodate single actor messages and all actors messages | 2 |  | 2017-03-14 | 2017-03-15 | 2017-03-14 | 2017-03-15 | Vignesh
|  |  | I want to see all the flows associated to my organization (Global Cockpit) | Refactor the message det page and the managed bean to include auto/manual dispatch flag | 2 |  | 2017-03-16 | 2017-03-17 | 2017-03-16 | 2017-03-17 | Vignesh
|  |  |  | Identify and implement domain model changes | 1 |  | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Vrinda
|  |  |  | Implement pages to display incidents based on AG and individual users | 1 |  | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | Vrinda
|  |  |  | Implement dispatch logic to be based on config data | 2 |  | 2017-03-03 | 2017-03-06 | 2017-03-03 | 2017-03-06 | Vrinda
|  |  |  | Implement assignment functionality and allocate to self functionality (DEPENDENT ON ROLES) | 2 |  | 2017-03-07 | 2017-03-08 | 2017-03-07 | 2017-03-08 | Vrinda
|  |  |  | Write test cases for dispatch logic, single actor, multiple actors, auto, manual combinations of messages | 1 |  | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | Vrinda
|  |  |  | Perform testing for all tasks above | 2 |  | 2017-03-10 | 2017-03-13 | 2017-03-10 | 2017-03-13 | Vrinda
MUST | IE-1442 | Flow page creator information display | I should only be able to view the personal details of the incident creator | Refactor the flow page to include the creator details in Timeline tab | 1 | 1 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Zhao
MUST | IE-1441 | Push notification | I should be notified when the incident is resolved or ready to test OR when the incident is assigned to me (PUSH NOTIF INTEGRATION) | Identify places where notifications need to be sent to users | 1 | 6 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | Zhao
|  |  |  | Configure FCM for Instant Edge and modify keys in Instant Edge | 1 |  | 2017-03-03 | 2017-03-03 | 2017-03-03 | 2017-03-03 | Zhao
|  |  |  | build and send out notifications | 1 |  | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | Zhao
|  |  |  | (Rigorous testing of Apps - Alpha) (Assume English only) | 2 |  | 2017-03-07 | 2017-03-08 | 2017-03-07 | 2017-03-08 | Zhao
|  |  |  | Write test cases and perform tests | 1 |  | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | Zhao
MUST | IE-1542 | Status cascading | Intended consequences of different UA types | Identify the statuses to be used in the flow components (flow,flowitem) | 1 | 4 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | Vrinda
|  |  |  | Map the user actions and flow and flow item status | 1 |  | 2017-03-15 | 2017-03-15 | 2017-03-15 | 2017-03-15 | Vrinda
|  |  |  | modify the existing logic and perform testing | 2 |  | 2017-03-16 | 2017-03-17 | 2017-03-16 | 2017-03-17 | Vrinda
MUST | IE-1528 | escalation | I should be able to define escalation procedure and trigger points (config data) (timer based AGD to escalate) | Refactor message det page to accommodate event based escalations | 1 | 6 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | Zhao
|  |  | I should be able to define a special User Action for end user to escalate the incident | Implement timer based event for escalation | 0
|  |  | I should be able to escalate the incident independent of its progress | Create page for configuring timer based escalation and actor group selection | 0
|  |  |  | Implement flow model domain changes to mark escalation procedure/step | 1 |  | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | Zhao
|  |  |  | Move event based escalation to new page | 1 |  | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | Zhao
|  |  |  | Implement the algorithm for new user action type "ESCASLATE" | 1 |  | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | Rameswari
|  |  |  | Write test cases to test escalations(Regression impacts to be tested as well) | 1 |  | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | Rameswari
|  |  |  | Perform testing for all tasks above | 1 |  | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | Rameswari
MUST | IE-1444 | user action | I should be able to put an incident on hold (to stop SLA counters) -- from root data User Action Consequence | Implement OnHold logic of user actions | 1 | 5.5 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | Zhao
|  |  | I should be able to withdraw/cancel an incident (incident creator) | Implement Withdraw/Cancel logic of user action | 1 |  | 2017-03-15 | 2017-03-15 | 2017-03-15 | 2017-03-15 | Zhao
|  |  | I should be able to log the cause or result of analysis (save a comment) ( log the resolution for an incident (marked as resolution)) | Implement Close logic of user action | 1 |  | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | Vignesh
|  |  |  | Make domain changes to accept resolution in case of close action | 1 |  | 2017-03-17 | 2017-03-17 | 2017-03-15 | 2017-03-15 | Vignesh
|  |  |  | write test cases to test close, onhold and withdraw/cancel | 0.5 |  | 2017-03-16 | 2017-03-16 | 2017-03-17 | 2017-03-17 | Rameswari
|  |  |  | Perform testing for all tasks above | 1 |  | 2017-03-16 | 2017-03-16 | 2017-03-17 | 2017-03-17 | Rameswari
MUST(LOW PRIORITY) | IE-1434 | Validation button -> deploy only after validation and undeploy when edit -> what happens to the existing flows? | I want to validate(dangling nodes, unassociated actors) and deploy a model (create flow only if validated) | Add a validate button to the Model Configuration page | 0.5 | 5.5
|  |  |  | Identify and Implement validation logic for the model | 1
|  |  |  | Identify and expose warnings to the UI on potential misconfiguration | 1
|  |  |  | Implement check on Model edit | 1
|  |  |  | Write unit test cases for Validation and deployment of flow model | 1
|  |  |  | Perform testing for all tasks above | 1
OPTIONAL | IE-1438 | Flow field group -> flow field control -> panels instead of tabs | I want to group fields (FFG) inorder to toggle (UI - +/-) selectFlow.xhtml | Add configuration options for collapsability in FFCs (in the table as new column) | 2 | 8
|  |  | I must be able to define if a Screen Layout Group is collapsed or opened in a particular Layout Control flowfieldcontrolDetermination.xhtml ; (Collapse which field groups?) | In the flow page, read configuration and collapse panels based on it | 1
|  |  |  | Refactor managed beans and add new methods to accommodate new requirements | 2
|  |  |  | Add exceptions, required converters and EJBs to handle transactions | 1
|  |  |  | Write unit test cases for FFG, FFC and Collapsibility and visibility | 1
|  |  |  | Perform testing for all tasks above | 1
67
Total No of Working day in Sprint 5 = 15 Days
No if of Hours per day = 8 Hr
No of Resource = 4
Total No of Man Hour for sprint 1= 10*8*4 = 480
Effort per person for Sprint Planning and retrospective =2 day
Total effort for Sprint Planning and Retrospective = 8*4 * 2= 64 Hr
Total hour Remaining = 480 – 64 = 416 Hr
Sprint Capacity = 416 Hr.
Total Effort required for all task in sprint = 67*8 = 536
Effort requied for the low priority user story = 5.5+ 8 = 13.5 days = 108
Total capacity of Sprint 5 = 536-108 = 428
Date | Rameswari | Vignesh | Zhao | Vrinda | Total Burndown
2017-03-01 | 8 | 8 | 8 | 8 | 32
2017-03-02 | 8 | 8 | 8 | 8 | 32
2017-03-03 | 9 | 9 | 9 | 9 | 36
2017-03-06 | 8 | 7 | 7 | 8 | 30
2017-03-07 | 9 | 10 | 10 | 9 | 38
2017-03-08 | 10 | 9 | 9 | 10 | 38
2017-03-09 | 9 | 10 | 10 | 9 | 38
2017-03-10 | 9 | 9 | 9 | 9 | 36
2017-03-13 | 8 | 8 | 8 | 8 | 32
2017-03-14 | 9 | 8 | 8 | 9 | 34
2017-03-15 | 9 | 9 | 9 | 9 | 36
2017-03-16 | 9 | 9 | 9 | 9 | 36
2017-03-17 | 9 | 9 | 9 | 9 | 36
454

## Sprint 6
Status | JIRA ID | Group | User Story | Task | Effort Estimate(days) | Total Estimate | Planned start Date | Planned End date | Actual start Date | Actual End date | Resource
MUST |  | Integration of Dashboard |  | Domain Model change( New Enum) | 0.5 | 7
|  |  |  | Dashboard page UI refactor -add new tiles for incident | 0.5
|  |  |  | Dashboard page UI refactor - refactor existing tiles | 0.5
|  |  |  | Refactor Create Change Page | 0.5
|  |  |  | Refactor Create Incident page | 0.5
|  |  |  | Refactor unified inbox to cater AG inbox | 0.5
|  |  |  | Create a new Backing bean for Incident | 1
|  |  |  | Refactor the current Flow Dashboard Managed bean | 1
|  |  |  | Testing the dashboard | 2
MUST |  | Tree |  | Java script implementation for Tree | 0.5 | 3.5
|  |  |  | UI implementation for Tree | 1
|  |  |  | Write Backing Bean for the UI | 1
|  |  |  | Testing for Tree | 1
MUST |  | Pick Up functionality Refactor |  | Move the pick functionality to edit button | 0.5 | 3
|  |  |  | Refactor Flow page UI | 0.5
|  |  |  | Withdraw Functionality refactor | 1
|  |  |  | Test the changes | 1

## Sprint Burndown 4-5
SPRINT 4 BURNDOWN
| Days | Planned Hours Burndown | Actual Hours burndown | Dates
| 0 | 320 | 348 | 2017-02-13
| 1 | 288 | 310 | 2017-02-14
| 2 | 256 | 274 | 2017-02-15
| 3 | 224 | 235 | 2017-02-16
| 4 | 192 | 200 | 2017-02-17
| 5 | 160 | 168 | 2017-02-18
| 6 | 128 | 130 | 2017-02-20
| 7 | 96 | 100 | 2017-02-21
| 8 | 64 | 72 | 2017-02-22
| 9 | 32 | 35 | 2017-02-23
| 10 | 0 | 0 | 2017-02-24
Variance = (348-320/320) *100 = 8.75
SPRINT 5 BURNDOWN
| Days | Planned Hours Burndown | Actual Hours burndown | Dates
| 0 | 416 | 454 | 2017-03-01
| 1 | 384 | 418 | 2017-03-02
| 2 | 352 | 382 | 2017-03-03
| 3 | 320 | 346 | 2017-03-06
| 4 | 288 | 312 | 2017-03-07
| 5 | 256 | 280 | 2017-03-08
| 6 | 224 | 244 | 2017-03-09
| 7 | 192 | 206 | 2017-03-10
| 8 | 160 | 168 | 2017-03-13
| 9 | 128 | 130 | 2017-03-14
| 10 | 96 | 100 | 2017-03-15
| 11 | 64 | 64 | 2017-03-16
| 12 | 32 | 32 | 2017-03-17
| 13 | 0 | 0 | 2017-03-18
Variance = (454-416/416) *100 = 9.13